## Read me
Programme tracker
⚠ GENERATED FILE — DO NOT EDIT. Regenerating overwrites everything here.
python3 scripts/generate_tracker.py
Why it is generated rather than maintained:
BACKLOG.md is the source of truth (project rule: documentation lives in git). A
hand-kept spreadsheet beside it becomes a second source that disagrees within a
fortnight — and then nobody knows which is right, which is worse than the problem
it was meant to solve. Edit the markdown, re-run the script, and they cannot drift.
What this fixes is a real complaint: 1,500 lines of markdown is the right tool for
the REASONING behind a story and the wrong one for "what is the status of
everything?". This gives the overview. The reasoning stays where it is — every row
carries its story id, so the detail is one search away in BACKLOG.md.
Counted right now:
Epics 22
Stories 226 (152 done, 1 in progress, 73 planned)
Delivered rows 7 (a story is only here if it has evidence)
Decisions 6
Defects 6
Open questions 5 of 11
Sheets:
Overview one row per epic — story counts and status
Stories one row per story — epic, wave, status, priority, the user story
Delivered what has actually shipped, with its test evidence and caveats
Decisions owner decisions, in his own words where they were recorded verbatim
Defects the register, with what is fixed, accepted and still open
Questions open questions and whether they have been answered
A caution about the Status column: it reflects what BACKLOG.md SAYS. That is a
deliberate limitation — this script reports the record, it does not audit it. If a
status is wrong here, the backlog is wrong, and that is the thing to fix.

## Overview
Epics
One row per epic. Story counts are distinct KAN ids.
Epic | Epic KAN id | Name | Status | Stories | Story ids | Notes from the backlog
EP17 |  | Family Tree Org Chart & Employee-Centric Navigation | Done | 7 | KAN-81 KAN-82 KAN-83 KAN-84 KAN-85 KAN-86 KAN-87 | ✅ Done
EP18 |  | Email Notification System | Done | 4 | KAN-88 KAN-89 KAN-90 KAN-91 | ✅ Done
EP19 |  | Full-Text Search | Done | 4 | KAN-92 KAN-93 KAN-94 KAN-95 | ✅ Done
EP20 |  | Vacation Calendar | Done | 3 | KAN-96 KAN-97 KAN-98 | ✅ Done
EP21 |  | Bulk Employee Import | Done | 4 | KAN-99 KAN-100 KAN-101 KAN-102 | ✅ Done
EP22 |  | Mobile Responsive Design | Done | 4 | KAN-103 KAN-104 KAN-105 KAN-106 | ✅ Done
EP23 |  | In-App Notification System | Done | 7 | KAN-107 KAN-108 KAN-109 KAN-110 KAN-111 KAN-112 KAN-113 | ✅ Done
EP24 |  | Vacation Cancellation & Withdrawal UI | Done | 5 | KAN-114 KAN-115 KAN-116 KAN-117 KAN-118 | ✅ Done
EP25 |  | Analytics & Reporting Dashboard | Done | 14 | KAN-119 KAN-120 KAN-121 KAN-122 KAN-123 KAN-124 KAN-125 KAN-126 KAN-127 KAN-128 KAN-129 KAN-130 KAN-131 KAN-132 | ✅ Done
EP26 |  | Vacation Balance Visibility | Done | 4 | KAN-133 KAN-134 KAN-135 KAN-136 | ✅ Done
EP27 |  | Employee Position Change Workflow | Done | 11 | KAN-137 KAN-138 KAN-139 KAN-140 KAN-141 KAN-142 KAN-143 KAN-144 KAN-145 KAN-146 KAN-147 | ✅ Done
EP28 |  | Security Hardening (Architecture Review) | In progress | 6 | KAN-148 KAN-149 KAN-150 KAN-151 KAN-152 KAN-153 | 🟡 In progress · ⏸ deferred to final stage S5 (D-004; KAN-153 excepted)
EP29 |  | Data Layer & Query Performance | In progress | 5 | KAN-154 KAN-155 KAN-156 KAN-157 KAN-158 | 🟡 In progress
EP30 |  | Scalability & Runtime | Planned | 6 | KAN-159 KAN-160 KAN-161 KAN-162 KAN-163 KAN-164 | ⬜ Planned
EP31 |  | Schema Source of Truth & Migrations | In progress | 3 | KAN-165 KAN-166 KAN-167 | 🟡 In progress
EP32 |  | Testing & CI Hardening | In progress | 4 | KAN-168 KAN-169 KAN-170 KAN-171 | 🟡 In progress
EP33 |  | Frontend Modernization | Blocked | 6 | KAN-172 KAN-173 KAN-174 KAN-175 KAN-176 KAN-177 | ⬜ Planned · ⏸ S5 (shares code with the escaping sweep; a11y applied as a design standard meanwhile — pending Q5)
EP34 |  | Architecture & Structure | Planned | 5 | KAN-178 KAN-179 KAN-180 KAN-181 KAN-182 | ⬜ Planned
EP38 |  | Employee Lifecycle Workflows | Done | 5 | KAN-183 KAN-184 KAN-185 KAN-186 KAN-187 | 🟡 In progress · first roadmap growth epic in the backlog (BG4) — build stage S3 (D-004); ✅ KAN-187 (audit), 🟡 KAN-185 (transfer); KAN-186 is Later
EP42 |  | Compensation, Job Architecture & Pay Equity (W0+W1 ✅ done; W2–W4 follow EP44 per D-010) | Done | 23 | KAN-188 KAN-189 KAN-190 KAN-191 KAN-192 KAN-193 KAN-194 KAN-195 KAN-196 KAN-197 KAN-198 KAN-199 KAN-200 KAN-201 KAN-202 KAN-203 KAN-204 KAN-206 KAN-207 KAN-208 KAN-209 KAN-210 KAN-218 | ⬜ Planned · BG7 — W0 builds in S2, W1–W4 in S3 (D-004). 23 stories in 5 waves (A1 · Wave-5 · A2 · A3 · A4–A6). ⚠ A6 overturned the pay/step model: the job decides the step, the step decides base pay, pay never decides the step. KAN-218 (additional pay) is new, KAN-209 is repurposed as the pay reconciliation, KAN-205 moved to Later, KAN-208 is conditional. Carries KAN-203, a P0 Critical…
EP44 |  | Performance Management (⚠ D-010 — BUILT FIRST, compensation follows; requirements OPEN, P0 written; ⚠ AMENDED BY A7 — goal types, milestones, the four-level scale, the enforced self-first ordering, and KAN-241 the readiness outcome) | Planned | 22 | KAN-219 KAN-220 KAN-221 KAN-222 KAN-223 KAN-224 KAN-225 KAN-226 KAN-227 KAN-228 KAN-229 KAN-230 KAN-231 KAN-232 KAN-233 KAN-234 KAN-235 KAN-236 KAN-237 KAN-238 KAN-239 KAN-240 | ⬜ Planned · BG7 · entered by A4/A5 — the owner chose full performance management over the 2-story input, accepting the delay in his own words (Decision D-006). 22 stories, stage S3, sequenced after EP42 and before EP43. Outline depth — entering S1, not build. Carries the EU AI Act / GDPR Art. 22 gate as stories (KAN-232, KAN-240), not notes, and works-council inspectability (KAN-238)
EP43 |  | Annual Compensation Review Cycle | Planned | 5 | KAN-211 KAN-213 KAN-214 KAN-215 KAN-216 | ⬜ Planned · BG7 · new in A2, reduced by A6 from 7 stories to 5. KAN-212 withdrawn (merged into KAN-216 and EP42's rate schedule); KAN-217 withdrawn (superseded by EP44). A6 collapsed the per-employee hike percentage, so this is now a round-management epic, not a differentiation one. Sequenced last, stage S3. The natural descope if S3 runs long

## Stories
Stories
One row per story. "Wave" and "Epic" come from the document structure, not a second list.
ID | Status | Epic | Wave / section | Priority | User story | Acceptance criteria (abridged)
KAN-12 | Done | EP1 — Authentication & Session Management |  | Must Have | As an employee, I want to log in with my work email so I can access the portal. | Login accepts email; invalid email shows error; redirects to dashboard on success.
KAN-13 | Done | EP1 — Authentication & Session Management |  | Must Have | As any logged-in user, I want my session to persist for 8 hours so I do not need to re-login constantly. | Session cookie TTL = 8 h; logout clears session immediately.
KAN-14 | Done | EP1 — Authentication & Session Management |  | Must Have | As any user, I want to log out securely so no one else can access my account on shared devices. | /logout clears session and redirects to login.
KAN-15 | Done | EP1 — Authentication & Session Management |  | Should Have | As a developer/demo, I want quick-access demo user tiles on the login page so testers can log in without credentials. | Login page shows up to 6 demo user cards; clicking one pre-fills email.
KAN-16 | Done | EP2 — Role-Based Access Control (RBAC) |  | Must Have | As a SYSTEM_ADMIN, I want to assign and revoke roles for any user so I can control access. | Role edit modal on admin panel; changes take effect immediately; own roles cannot be removed.
KAN-17 | Done | EP2 — Role-Based Access Control (RBAC) |  | Must Have | As a SYSTEM_ADMIN, I want to enable or disable a user account so ex-employees cannot log in. | Toggle active/inactive; inactive users are rejected at login with clear error.
KAN-18 | Done | EP2 — Role-Based Access Control (RBAC) |  | Must Have | As a non-admin user, I want to be redirected with an error message if I try to access a restricted page. | HTTP redirect to dashboard with flash error; no data leaked.
KAN-19 | Done | EP2 — Role-Based Access Control (RBAC) |  | Should Have | As a SYSTEM_ADMIN, I want the admin panel to show all users with their roles and last-login timestamp. | Admin panel loads all users; shows role badges; shows "Never" if no login recorded.
KAN-20 | Done | EP3 — Employee Registry & Directory |  | Must Have | As an HR_ADMIN / SYSTEM_ADMIN, I want to register a new employee through a guided multi-step form so data is captured completely. | 6-step form: Personal Info → Employment → Organisation → Reporting → Skills → Portal Access; auto-generates EMP-XXX number; creates all records atomically.
KAN-21 | Done | EP3 — Employee Registry & Directory |  | Must Have | As a registrar, I want the employee number to be auto-generated sequentially so I don't assign duplicates. | _next_employee_number() selects MAX and increments; zero-pads to 3 digits.
KAN-22 | Done | EP3 — Employee Registry & Directory |  | Must Have | As an HR_ADMIN, I want to search and filter the employee directory by name, location, business unit, and employment type. | Filters applied server-side; results paginate at configurable rows/page.
KAN-23 | Done | EP3 — Employee Registry & Directory |  | Should Have | As a SYSTEM_ADMIN / HR_ADMIN, I want to see each employee's manager, location, skills, and certifications in the directory row. | Directory table includes manager pill, location badge, skill bars, cert count.
KAN-24 | Done | EP3 — Employee Registry & Directory |  | Must Have | As a registrar, I want to assign solid-line and dotted-line managers to a new employee during registration. | Step 4 lets user search and select solid/dotted manager; records written to manager_relationships with is_current=true.
KAN-25 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As any employee, I want to view my complete profile including employment details, org placement, manager, skills, and certifications. | /profile loads own profile; /profile/<id> loads others; is_own flag controls edit UI.
KAN-26 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As an employee, I want to add skills to my profile and self-rate each on a 1–10 scale so my competencies are visible. | Skill modal with 🌱💡⚡🏆 level buttons; POST /api/profile/skills; list refreshes in-page.
KAN-27 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As an employee, I want to remove a skill from my profile so outdated entries do not mislead others. | DELETE /api/profile/skills/<id>; list updated in-page.
KAN-28 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As an employee, I want to add certifications with issuer, dates, and credential URL so my qualifications are recorded. | POST /api/profile/certifications; accepts cert name, provider, dates, URL; in-page reload.
KAN-29 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As an employee, I want to edit and remove my certifications so I keep them current. | PUT and DELETE /api/profile/certifications/<id>; in-page update.
KAN-30 | Done | EP4 — Employee Profile & Self-Service |  | Must Have | As an employee, I want to record my gender on my profile so my vacation eligibility is calculated correctly. | Gender dropdown (Male/Female/Other) with auto-save on change via POST /api/profile/gender.
KAN-31 | Done | EP4 — Employee Profile & Self-Service |  | Should Have | As a SYSTEM_ADMIN / HR_ADMIN, I want to validate an employee's skill rating so the profile shows verified competencies. | POST /api/admin/validate-skill; status → VALIDATED; skill bar turns green.
KAN-32 | Done | EP5 — Organisational Structure |  | Must Have | As a SYSTEM_ADMIN, I want to register companies so multiple entities can share the portal. | /admin/companies CRUD; company has name, industry, website, HQ, description, active flag.
KAN-33 | Done | EP5 — Organisational Structure |  | Should Have | As an employee, I want to view my company's overview page showing headcount, locations, and business units. | /company shows stats, BU breakdown, location breakdown; accessible to all employees.
KAN-34 | Done | EP5 — Organisational Structure |  | Must Have | As an HR_ADMIN, I want to assign employees to business units, functional units, locations, and cost centres during onboarding. | Registration step 3 has cascading BU → FU selectors; employee_org_assignments written with is_current=true.
KAN-35 | Done | EP5 — Organisational Structure |  | Must Have | As a manager or admin, I want to view the org hierarchy as an interactive tree so I can understand reporting lines. | /org-tree renders recursive tree via CTE (max 10 levels); nodes clickable; expand/collapse; admin can pick any root or Full Org.
KAN-36 | Done | EP5 — Organisational Structure |  | Should Have | As a manager, I want to see pending vacation badges on org tree nodes so I know which reportees need action. | Orange ⏳ badge on nodes with pending requests; links to /vacation/team.
KAN-37 | Done | EP6 — Manager Self-Service |  | Must Have | As a manager, I want to see all my direct reports in a card layout with their role, location, skills, and manager links. | /my-team shows cards for all SOLID_LINE direct reports; each card has profile link and management quick-actions.
KAN-38 | Done | EP6 — Manager Self-Service |  | Should Have | As a manager, I want to see a pending vacation count badge on each team member's card so I can act without leaving the team page. | pendingCounts fetched on page load; badge shows ⏳ N vacation req with link to /vacation/team.
KAN-39 | Done | EP7 — Vacation & Leave Management |  | Must Have | As a SYSTEM_ADMIN, I want to define vacation types per company (e.g. Annual Leave, Sick Leave) with day limits and paid/unpaid flags. | /admin/vacation-types CRUD; name, max days/year, is_paid, colour, description stored per company.
KAN-40 | Done | EP7 — Vacation & Leave Management |  | Must Have | As a SYSTEM_ADMIN, I want to make a vacation type available only to employees in specific locations. | Multi-select locations; stored in vacation_type_locations; company-wide types have no location entries.
KAN-41 | Done | EP7 — Vacation & Leave Management |  | Must Have | As a SYSTEM_ADMIN, I want to add eligibility rules (gender, minimum tenure) to vacation types so the right employees see them. | Step 4 Rules builder; supports GENDER_EQ, MIN_TENURE_MONTHS, MIN_TENURE_YEARS; AND logic.
KAN-42 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I want to see only the vacation types I am eligible for so I don't waste time applying for unavailable leave. | Location + ALL rules must pass; rule labels shown as purple badges; ineligible types hidden.
KAN-43 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I want to see my used vs. remaining days for each vacation type so I know my balance. | Type cards show used/max progress bar; remaining shown in request modal; counts PENDING+APPROVED.
KAN-44 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I want to submit a vacation request with start/end dates and a note so my manager is notified. | Request modal; weekday count verified server-side; manager auto-set from solid-line; annual limit enforced.
KAN-45 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I want to cancel a PENDING request if my plans change. | DELETE /api/vacation/request/<id>; only PENDING status can be cancelled; status → CANCELLED.
KAN-46 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I cannot submit a vacation request if I have no manager assigned. | Warning banner shown; request button disabled; API returns 400 with reason.
KAN-48 | Done | EP7 — Vacation & Leave Management |  | Must Have | As an employee, I want to see all my past and current requests with their status and manager note. | Request history table shows type, dates, days, status badge, manager note, cancel button for PENDING.
KAN-49 | Done | EP7 — Vacation & Leave Management |  | Must Have | As a manager, I want to see all pending vacation requests from my reportees and approve or reject them with a note. | Pending tab; review modal with optional note; POST /api/vacation/review/<id>; only PENDING reviewable.
KAN-50 | Done | EP7 — Vacation & Leave Management |  | Should Have | As a manager, I want to see my team's upcoming approved leave in a calendar-like schedule so I can plan coverage. | Upcoming tab groups by month; "● On leave" indicator for currently active requests.
KAN-51 | Done | EP7 — Vacation & Leave Management |  | Must Have | As a manager, I cannot approve a request that has already been reviewed. | API validates status == PENDING before update; returns 400 if already actioned.
KAN-52 | Done | EP8 — Company Branding & Theming |  | Must Have | As a SYSTEM_ADMIN, I want to upload a company logo so it appears in the sidebar for all employees of that company. | Drag-and-drop upload; saved to static/uploads/logos/; old file deleted on replacement; PNG/JPG/SVG/WebP max 2 MB.
KAN-53 | Done | EP8 — Company Branding & Theming |  | Should Have | As a SYSTEM_ADMIN, I want to optionally provide an external logo URL instead of uploading a file. | Tab switcher between Upload File and External URL; live preview; uploaded file takes priority.
KAN-54 | Done | EP8 — Company Branding & Theming |  | Must Have | As a SYSTEM_ADMIN, I want to set a primary theme colour for my company so the portal reflects our brand identity. | Colour picker + hex input + 8 quick presets; saved as theme_color; injected as --primary CSS variable.
KAN-55 | Done | EP8 — Company Branding & Theming |  | Should Have | As a SYSTEM_ADMIN, I want to add a company-wide header banner (HTML) above all portal pages for announcements. | header_html field; rendered above all pages for company employees; inline preview button.
KAN-56 | Done | EP8 — Company Branding & Theming |  | Should Have | As a SYSTEM_ADMIN, I want to add a company-wide footer (HTML) below all pages for legal links and support contacts. | footer_html field; rendered at bottom of all pages; clear button available.
KAN-57 | Done | EP8 — Company Branding & Theming |  | Must Have | As any employee, I want to switch between light and dark mode so I can work comfortably in different environments. | Toggle button in topbar; instant CSS variable swap; POST /api/user/theme persists to DB; restored on next login.
KAN-58 | Done | EP8 — Company Branding & Theming |  | Should Have | As an employee, my branding is refreshed in my session after the admin updates the company record. | admin_company_edit POST re-fetches and updates session['branding'] immediately.
KAN-59 | Done | EP9 — Dashboard & Real-Time Metrics |  | Must Have | As any logged-in user, I want to see a dashboard with the key stats relevant to my role so I get an immediate status overview. | Stats differ by role; SYSTEM_ADMIN sees all-company counts; managers see team counts; employees see personal stats.
KAN-60 | Done | EP9 — Dashboard & Real-Time Metrics |  | Should Have | As a dashboard user, I want stat cards to auto-refresh periodically so I see live data without reloading. | Refresh interval configurable per role; JS polls /api/dashboard/stats; changed values animate (flash green).
KAN-61 | Done | EP9 — Dashboard & Real-Time Metrics |  | Should Have | As a dashboard user, I want clickable stat cards that filter the employee directory to the relevant subset. | Clicking a stat card navigates to /directory?filter=<value>; directory pre-applies the filter.
KAN-62 | Done | EP9 — Dashboard & Real-Time Metrics |  | Nice to Have | As a SYSTEM_ADMIN, I want to configure per-role refresh intervals so I can balance data freshness against server load. | POST /api/admin/refresh-settings; persisted to widget_refresh_settings; applied on next page load.
KAN-63 | Done | EP10 — Work Anniversary Recognition |  | Should Have | As a manager or admin, I want to see a visual indicator next to employees whose work anniversaries are upcoming so I can acknowledge them. | 🎂 badge computed from join_date; urgency levels: normal (>7 days), soon (≤7 days), urgent (today/tomorrow); animated per urgency.
KAN-64 | Done | EP10 — Work Anniversary Recognition |  | Should Have | As a manager, I want to hover over the badge to see the exact anniversary date and tenure. | Tooltip shows "N-year anniversary on DD MMM YYYY" on hover with smooth animation.
KAN-65 | Done | EP11 — Two-Tier Admin System |  | Must Have | As a platform owner, I want a Tech Admin role that spans all companies so I can manage the entire portal from one account. | SYSTEM_ADMIN role grants full cross-company access; not affiliated with any company; company_id = NULL on employee record.
KAN-66 | Done | EP11 — Two-Tier Admin System |  | Must Have | As an HR Director, I want a Portal Admin role scoped to my company so I can self-manage my company's data without impacting others. | PORTAL_ADMIN role; all admin queries auto-filter by session['company_id']; cannot see other companies' data.
KAN-67 | Done | EP11 — Two-Tier Admin System |  | Must Have | As a Tech Admin, I want to switch company context in the Admin Panel so I can manage a specific company's data without separate logins. | Company context bar in admin header; selecting a company filters all admin sections; selecting "All Companies" removes filter; stored in session['admin_company_id'].
KAN-68 | Done | EP11 — Two-Tier Admin System |  | Must Have | As a Tech Admin, I should not belong to any company so there is no data-isolation conflict. | scripts/setup_db.py sets company_id = NULL on all SYSTEM_ADMIN employee records; new Tech Admin registrations must have no company; session['company_id'] is empty.
KAN-69 | Done | EP12 — Multi-Company Org CRUD |  | Must Have | As a Portal Admin, I want to add, edit, and delete Business Units for my company so I can keep the org chart accurate. | POST/PUT/DELETE /api/admin/org/business-units; company_id auto-injected; 409 if employees assigned on delete; Edit modal pre-filled from live data.
KAN-70 | Done | EP12 — Multi-Company Org CRUD |  | Must Have | As a Portal Admin, I want to add, edit, and delete Locations so I can track where employees are based. | POST/PUT/DELETE /api/admin/org/locations; office_code unique per instance; 409 on delete if employees assigned.
KAN-71 | Done | EP12 — Multi-Company Org CRUD |  | Must Have | As a Portal Admin, I want to add, edit, and delete Functional Units, linking each to a Business Unit so the hierarchy is complete. | POST/PUT/DELETE /api/admin/org/functional-units; BU dropdown in FU modal populated from live BU list; cross-company write blocked with 403.
KAN-72 | Done | EP12 — Multi-Company Org CRUD |  | Should Have | As a Tech Admin, I want to manage org structure for any company I select in the context switcher so I can assist Portal Admins. | Tech Admin in company context can CRUD org entries for that company; Tech Admin with "All Companies" selected can see all entries.
KAN-73 | Done | EP13 — Feature-Level Permission Matrix |  | Must Have | As a Tech Admin, I want to define what each role can read, write, and delete for each portal feature so access can be tuned without code changes. | Roles & Permissions tab with 8 feature rows × all roles × R/W/D checkboxes; changes saved via POST /api/admin/roles/feature-access; SYSTEM_ADMIN row locked.
KAN-74 | Done | EP13 — Feature-Level Permission Matrix |  | Must Have | As a Tech Admin, I want permission changes to take effect immediately so I do not need to restart the server. | upsert via ON CONFLICT DO UPDATE; no server restart required; UI reverts checkbox on API failure.
KAN-75 | Done | EP14 — Test Automation & Quality Gates |  | Must Have | As a developer, I want a pre-commit hook that runs all tests so regressions cannot reach the repository. | .git/hooks/pre-commit runs pytest tests/ -q; aborts commit on failure; 238 tests in ≤ 1 second.
KAN-76 | Done | EP14 — Test Automation & Quality Gates |  | Must Have | As a developer, I want UI/UX regression tests that catch broken template assets so login page breakages are caught before commit. | test_ui_ux.py verifies CSS path (css/style.css), all login page CSS classes exist in stylesheet, no old class names remain, admin tab visibility per role.
KAN-77 | Done | EP14 — Test Automation & Quality Gates |  | Must Have | As a developer, I want integration tests for all admin CRUD endpoints including company scoping so security boundaries are continuously verified. | test_routes_org.py — company filter in query params for Portal Admin, 403 cross-company write, 409 on delete with employees, context switch sets session.
KAN-78 | Done | EP15 — Login Page Redesign |  | Should Have | As a new user, I want a professional login page that communicates product value so I trust the portal. | Split-panel: left hero with gradient, tagline, 4 feature bullets; right panel with form, title, footer. Responsive (hero collapses on mobile).
KAN-79 | Done | EP15 — Login Page Redesign |  | Should Have | As a demo/tester, I want one-click demo account chips so I can log in without typing an email. | 2-column grid of demo cards; each shows name, title, role badge; clicking auto-submits the form; quickLogin() JS function.
KAN-80 | Done | EP16 — Multi-Company Seed Data (Telia) |  | Should Have | As a Tech Admin, I want realistic employee data for a second company (Telia) so I can demonstrate multi-company features to stakeholders. | scripts/setup_db.py seeds 100 Telia employees across 5 BUs, 5 locations, 12 FUs; full management hierarchy; user accounts with correct roles; Portal Admin seeded as Maria Andersson.
KAN-81 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As an employee, I want the org tree to start from my own position so I immediately see my place in the hierarchy. | Tree always loads rooted at session['employee_id']; "you" node is highlighted in purple; route is @login_required (all roles).
KAN-82 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As an employee, I want to navigate up the tree to see my manager's team so I understand the wider org context. | Blue ↑ button shows direct manager name; clicking re-focuses the tree at the manager's node; breadcrumb trail updates.
KAN-83 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As a manager, I want to navigate down into a specific person's team so I can review their reporting structure. | Focus ↓ button visible on hover for any node with reports; clicking re-focuses tree at that person; ← My view button returns.
KAN-84 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As any user, I want a breadcrumb trail showing my path through the org so I can jump to any ancestor level. | Breadcrumb renders all ancestors from CEO to current focus; each ancestor is a clickable button; current focus shown in bold.
KAN-85 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As any user, I want the chart to look like a family tree with connecting lines so the hierarchy is visually clear. | Top-down layout: parent card → vertical stem → horizontal connector → child cards; T-connector lines drawn with CSS pseudo-elements; no SVG or canvas required.
KAN-86 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As a developer, I want a /api/org-tree/context endpoint so the frontend can fetch ancestor chains without loading the entire tree. | Returns { focus: {...}, ancestors: [{...}, ...] } ordered CEO-first; uses upward recursive CTE; no depth limit (org is finite).
KAN-87 | Done | EP17 — Family Tree Org Chart & Employee-Centric Navigation |  | Must Have | As a developer, I want integration tests covering the new context endpoint and family tree page so regressions are caught pre-commit. | TestOrgTreePage (6 tests): accessible to all roles, contains ftree-root and org-nav. TestApiOrgTree (4 tests): root param, empty tree, redirect. TestApiOrgTreeContext (5 tests): ancestors, no ancestors at top, default to session, null focus.
KAN-88 | Done | EP18 — Email Notification System |  | Must Have | As a Company Admin, I want to configure which roles receive which notification events so that only relevant people are alerted. | Admin matrix UI shows events × roles; checkboxes for enabled + allow_mute; saved via POST /api/notifications/settings.
KAN-89 | Done | EP18 — Email Notification System |  | Must Have | As a Company Admin, I want to propagate notification settings down the role hierarchy so I don't configure each role individually. | inherit=true on POST propagates to all sub-roles via ROLE_HIERARCHY map.
KAN-90 | Done | EP18 — Email Notification System |  | Should Have | As an Employee, I want to mute non-critical notifications so I am not overwhelmed. | POST /api/notifications/mute; only works if allow_mute=true in company config.
KAN-91 | Done | EP18 — Email Notification System |  | Must Have | As a Developer, I want async email sending so HTTP requests are never blocked by SMTP. | threading.Thread sends email outside request lifecycle; SMTP_HOST empty = log-only dev mode.
KAN-92 | Done | EP19 — Full-Text Search |  | Must Have | As an Employee, I want to search for colleagues by name or job title so I can find them quickly. | GET /api/search?q= uses plainto_tsquery on GIN-indexed employee_search_index; returns ranked results.
KAN-93 | Done | EP19 — Full-Text Search |  | Should Have | As an Employee, I want to search for my upcoming vacations in natural language. | "my upcoming vacation", "next month" patterns parsed server-side to date-range queries.
KAN-94 | Done | EP19 — Full-Text Search |  | Should Have | As a Manager, I want to type "people reporting to me" and see my org tree. | Pattern matching returns focus_tree action with root_id=my employee_id.
KAN-95 | Done | EP19 — Full-Text Search |  | Must Have | As any user, I want a search bar always visible in the topbar. | .topbar-search form present on all authenticated pages; links to /search results page.
KAN-96 | Done | EP20 — Vacation Calendar |  | Must Have | As an Employee, I want a month-grid calendar of my leave so I can see my planned absences at a glance. | /vacation/calendar renders pure CSS/JS month grid; scope=mine shows own approved+pending requests.
KAN-97 | Done | EP20 — Vacation Calendar |  | Must Have | As a Manager, I want to see my whole team's leave in the calendar so I can plan workload. | scope=team queries manager_relationships for solid-line reports; all their approved+pending requests shown.
KAN-98 | Done | EP20 — Vacation Calendar |  | Should Have | As an Admin, I want to see company-wide leave in the calendar. | scope=all scoped to company_id; colour legend auto-generated from vacation type colours.
KAN-99 | Done | EP21 — Bulk Employee Import |  | Must Have | As a Portal Admin, I want to import employees from a CSV so I can onboard large teams at once. | Drag-drop upload → row-level validation → preview → auto-approve (zero errors) → process.
KAN-100 | Done | EP21 — Bulk Employee Import |  | Must Have | As an HR Admin, I want to upload a CSV that goes through an approval workflow before employees are created. | HR Admin uploads → status=PENDING_REVIEW → Portal Admin approves → process.
KAN-101 | Done | EP21 — Bulk Employee Import |  | Must Have | As a Portal Admin, I want to review and reject an HR Admin's import if it contains errors. | POST /api/admin/imports/<id>/reject with reason; import marked REJECTED.
KAN-102 | Done | EP21 — Bulk Employee Import |  | Must Have | As a Developer, I want per-row validation so that a few bad rows don't block the entire import. | Each row gets validation_errors JSONB; VALID rows imported independently of INVALID rows.
KAN-103 | Done | EP22 — Mobile Responsive Design |  | Must Have | As a Mobile User, I want the sidebar to open as a drawer so I can navigate on a phone. | @media <768px: sidebar transform translateX(-100%); hamburger toggles .mob-open; overlay closes it.
KAN-104 | Done | EP22 — Mobile Responsive Design |  | Must Have | As a Mobile User, I want data tables to show as labelled cards so I can read them without horizontal scroll. | .data-table td becomes display:flex with ::before content:attr(data-label).
KAN-105 | Done | EP22 — Mobile Responsive Design |  | Should Have | As a Mobile User, I want the org tree to scroll horizontally with touch momentum. | .ftree-wrap: overflow-x:auto; -webkit-overflow-scrolling:touch.
KAN-106 | Done | EP22 — Mobile Responsive Design |  | Should Have | As a Mobile User, I want the login page to stack vertically so it's usable on a small screen. | .login-wrap flex-direction:column at <768px; hero collapses to 180px.
KAN-107 | Done | EP23 — In-App Notification System |  | Must Have | As an employee, I want a bell notification when my vacation is approved so I know without checking my history. | user_notifications row inserted for employee on every approve/reject; bell badge count > 0 after approval; message includes type, dates.
KAN-108 | Done | EP23 — In-App Notification System |  | Must Have | As an employee, I want to see the approval notification in the bell dropdown so I can read the outcome without navigating away. | Bell dropdown renders "My Notifications" section; shows ✅/❌ icon, message text, timestamp, and "View →" link to /vacation.
KAN-109 | Done | EP23 — In-App Notification System |  | Must Have | As a manager, I want a bell notification when an employee cancels their vacation so I can replan team capacity. | VACATION_CANCELLED event creates user_notifications row for manager's user_id; message names the employee and dates; link /vacation/team.
KAN-110 | Done | EP23 — In-App Notification System |  | Must Have | As any user, I want the bell badge to show the total of pending approvals plus unread notifications so one badge covers everything. | loadBellCount() fetches /api/vacation/pending-count and /api/my-notifications in parallel; badge = sum of both.
KAN-111 | Done | EP23 — In-App Notification System |  | Should Have | As any user, I want notifications to auto-mark as read after I open the dropdown so the badge clears without a manual action. | setTimeout(() => fetch('/api/my-notifications/mark-read', {method:'POST'}), 2000) fires after dropdown opens.
KAN-112 | Done | EP23 — In-App Notification System |  | Must Have | As a developer, I want /api/my-notifications and /api/my-notifications/mark-read endpoints so the frontend can fetch and clear alerts. | GET returns {count, notifications:[]} with event_type, message, link, created_at; POST marks all read for current user.
KAN-113 | Done | EP23 — In-App Notification System |  | Must Have | As a developer, I want unit tests verifying notifications are created on approve, reject, and cancel so regressions are caught pre-commit. | test_approve_sets_approved_status asserts create_user_notification called with correct user_id, event, message; same for reject and cancel; no-crash test when user account missing.
KAN-114 | Done | EP24 — Vacation Cancellation & Withdrawal UI |  | Must Have | As an employee, I want a clearly visible "✕ Cancel" button next to PENDING requests so I can cancel without hunting for a hidden control. | Button styled as btn btn-danger btn-sm; red background, white text; visible in request history table; confirmation dialog says "Your manager will be notified."
KAN-115 | Done | EP24 — Vacation Cancellation & Withdrawal UI |  | Should Have | As an employee, I want to withdraw an approved vacation that hasn't started yet so I can change my plans. | "Withdraw" button appears on APPROVED rows where start_date > today; DELETE endpoint accepts APPROVED + future; confirmation warns "This cannot be undone."
KAN-116 | Done | EP24 — Vacation Cancellation & Withdrawal UI |  | Must Have | As the system, I want to block withdrawal of already-started vacations so approved leave cannot be retroactively removed. | DELETE returns 400 "Cannot withdraw a request that has already started" if start_date <= today.
KAN-117 | Done | EP24 — Vacation Cancellation & Withdrawal UI |  | Must Have | As a manager, I want a bell notification and email when an employee cancels or withdraws so I can adjust team plans. | VACATION_CANCELLED dispatch + create_user_notification called from api_vacation_cancel; manager's user_id resolved from vacation_requests.manager_id; link = /vacation/team.
KAN-118 | Done | EP24 — Vacation Cancellation & Withdrawal UI |  | Must Have | As a developer, I want unit tests for all cancellation/withdrawal paths so edge cases are covered. | Tests: cancel PENDING succeeds; withdraw future APPROVED succeeds; already-started APPROVED blocked (400); REJECTED blocked (400); no-crash when manager has no user account; notification link is /vacation/team.
KAN-119 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want page-visit tracking so I know which features employees actually use. | page_views table; @after_request hook logs user_id, company_id, role, route, page_label in a background thread; skips /api/, /static/, login, unauthenticated requests.
KAN-120 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want search-query logging so I can identify what employees can't find. | search_logs table; every /api/search call logs query, result_count, role, company_id in background thread.
KAN-121 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want an Overview tab showing daily active users, most-visited pages, and feature adoption % so I understand portal engagement. | Chart.js line chart for DAU; horizontal bar for feature adoption (% of employees who visited each feature); top-pages table; bulk-import usage widget.
KAN-122 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want a Vacation tab with KPIs (approval rate, avg decision time, pending backlog), time-series chart, status doughnut, and per-employee drilldown. | Approval/rejection/cancellation rates; avg manager decision hours; requests-over-time line chart; status doughnut; leave utilisation grouped by Company/Dept/Location/Manager; sortable employee table with used-days column.
KAN-123 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want a Skills tab showing profile completeness %, validation rate, top skills, and skills-added trend so I understand the talent data quality. | KPI: employees with ≥1 skill / total; validation rate; bar chart of skills added per month; horizontal bar of top 15 skills; per-employee skill-count table.
KAN-124 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want an Org Chart tab with headcount KPIs, org depth, span of control, headcount growth line chart, and org-chart page view trend so I understand structure health and feature usage. | KPIs: active headcount, manager count, avg span, max depth, org-chart views in period; headcount by department bar; headcount growth line; manager span-of-control sortable table.
KAN-125 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want a Search tab showing top queries, zero-result rate, and a "zero-result terms" table so I can act on content gaps. | KPIs: total searches, unique searchers, zero-result rate; search volume over time; top-10 terms bar; full terms table; dedicated zero-result table.
KAN-126 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want to filter all analytics by date preset (30d / 90d / 1yr) or a custom range so I can compare periods. | Pill buttons for presets; custom date range reveals two date inputs; filter change invalidates cache and reloads current tab data.
KAN-127 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As a Super Admin, I want a company dropdown so I can view analytics for any onboarded company. | Company <select> shown only for SYSTEM_ADMIN; resolves to ?company_id=; PORTAL_ADMIN and HR_ADMIN always see their own company.
KAN-128 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an admin, I want to download any tab's data as a CSV so I can share it in board meetings. | /api/analytics/export/csv?section=<tab> returns text/csv with correct filename; tested for vacation (employee drilldown) and search (top terms).
KAN-129 | Done | EP25 — Analytics & Reporting Dashboard |  | Should Have | As an admin, I want to print any analytics view as a PDF using the browser print dialog. | Print button calls window.print(); @media print CSS hides sidebar, topbar, bell, and filter bar; all tab content visible; chart cards break-inside: avoid.
KAN-130 | Done | EP25 — Analytics & Reporting Dashboard |  | Should Have | As an admin, I want filter state to be reflected in the URL so I can share a specific view with a colleague. | All filter params (tab, range, start, end, company_id, group_by) in query string via history.replaceState; page restores state on load.
KAN-131 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As an HR Admin, I want read-only access to my company's analytics so I can track leave and skills without needing Company Admin rights. | HR_ADMIN added to _ROLES tuple in analytics route; sidebar "Analytics" link visible for HR_ADMIN; company always scoped to session.
KAN-132 | Done | EP25 — Analytics & Reporting Dashboard |  | Must Have | As a developer, I want 24 unit tests covering all analytics endpoints so access control, data shape, CSV export, and date parsing are verified. | TestAnalyticsPageAccess (5), TestAnalyticsOverview (5), TestAnalyticsVacation (3), TestAnalyticsSkills (2), TestAnalyticsOrg (2), TestAnalyticsSearch (2), TestAnalyticsExport (3), TestAnalyticsDateParsing (2) — all passing.
KAN-133 | Done | EP26 — Vacation Balance Visibility |  | Must Have | As an employee, I want each vacation type card to show how many days I have left so I can plan at a glance. | /vacation cards render "X days left" (in the type colour) next to "used / annual limit"; types with no cap show "No annual limit".
KAN-134 | Done | EP26 — Vacation Balance Visibility |  | Must Have | As an employee, I want the request modal to show my remaining balance for the selected type, updating as I pick dates, so I know the impact before submitting. | Selecting a type shows "N of MAX days remaining this year"; after dates it adds "this request uses D days → R will remain"; panel turns red with a warning when D > remaining.
KAN-135 | Done | EP26 — Vacation Balance Visibility |  | Must Have | As a manager, I want each pending request to show the employee's remaining balance for that type so I can spot over-allocation in the list. | /api/vacation/team-pending returns max_days + used_days; pending row shows "used/limit left" and flags "⚠ over limit" in red when exceeded.
KAN-136 | Done | EP26 — Vacation Balance Visibility |  | Must Have | As a manager, I want the approve/reject modal to state the balance and post-approval remainder so my decision is informed. | Review modal shows "<name> has N of MAX <type> days left. Approving this D-day request leaves R days."; red warning when it would exceed the limit.
KAN-137 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As a manager, I want to drag an employee onto another person in the Org Tree to propose a move so the change starts where I already work. | .ft-card is draggable only when has_feature_access('org_change','w'); dropping S on T opens a "Request Position Change" modal pre-filled from T (new manager + unit/location).
KAN-138 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As a requester, I want to adjust the proposed business unit, department, location, and manager and give a reason before submitting so the request is accurate. | Modal selects populated from /api/org-change/prefill (company-scoped); reason is mandatory; submit POST /api/org-change/request; banner states nothing changes until approved.
KAN-139 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As the system, I want to prevent an individual employee from initiating their own move so moves are always manager-driven. | POST /api/org-change/request gated by org_change (write); requester must manage the subject (solid-line) or be HR/Portal/System admin, else 403; plain EMPLOYEE blocked.
KAN-140 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As a Portal Admin, I want to configure how many approval levels a move needs and who approves each so the workflow matches our governance. | /admin/org-change-workflow editor adds/removes ordered levels; each level is Role (company role) or Person (employee); replace-all save via POST /api/admin/org-change-workflow.
KAN-141 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As an approver, I want to see only the requests waiting at a step I can decide so my queue is relevant. | /api/org-change/pending returns requests where the current step matches the caller's role or employee id; shown in "Pending My Approval" with the from→to diff and "Level X / N".
KAN-142 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As an approver, I want to approve or reject with a note so the next level or the requester understands the decision. | POST /api/org-change/<id>/decide records the step decision; approve with more levels advances current_step; final approve applies the change; reject stops the chain.
KAN-143 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As the system, I want approvals to be strictly sequential and any rejection to stop the chain so partial moves never occur. | Level N+1 is only notified after level N approves; a single reject sets status=REJECTED and applies no change; verified in tests and end-to-end.
KAN-144 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As the system, I want the final approval to actually move the employee so the org data reflects the decision. | apply_change sets old employee_org_assignments.is_current=FALSE, inserts a new current row (BU/FU/location, cost centre carried), and re-points the SOLID_LINE manager when changed.
KAN-145 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As a requester and employee, I want to be notified at every step so I know the status. | In-app notifications on submit, each level pass, final approve, and reject (ORG_CHANGE_* events, link /org-change) to requester; subject notified on final approve and reject.
KAN-146 | Done | EP27 — Employee Position Change Workflow |  | Should Have | As a requester, I want to see my requests and cancel a pending one so I stay in control. | "My Requests" tab shows status + current level; POST /api/org-change/<id>/cancel allowed for the requester or an admin on PENDING only.
KAN-147 | Done | EP27 — Employee Position Change Workflow |  | Must Have | As a developer, I want unit tests covering permissions and the sequential engine so regressions are caught pre-commit. | tests/test_org_change.py (17): initiator matrix, decide advance/reject/final, approver eligibility, apply_change SQL, create_request notifications, workflow save; full suite 4,511 passing.
KAN-148 | Planned | EP28 — Security Hardening |  | Must Have (pre-prod) | As the product owner, I want real authentication (password hash / SSO-OIDC / signed magic-link) so a session cannot be minted from an email address alone. (F1) | Login requires a verified factor; no session issued on email-only match; the login page no longer renders real user emails to anonymous visitors; existing tests updated.
KAN-149 | Planned | EP28 — Security Hardening |  | Must Have (pre-prod) | As the system, I want CSRF protection on every state-changing endpoint so cross-site requests cannot act as a logged-in user. (F2) | Flask-WTF CSRFProtect (or a double-submit token for JSON) added as a real dependency; token required on all POST/PUT/DELETE (~44 routes); api.js sends the token; tests cover accept/reject.
KAN-150 | In progress | EP28 — Security Hardening |  | 🟡 Partial (directory, org-tree, team,… | As the system, I want all dynamic values escaped before insertion into the DOM so stored data cannot execute as script. (F3) | Every innerHTML build routes through a shared escapeHtml/safe-html\\ helper (or textContent); directory, org-tree, team, my-team, admin panels covered; regression test with a <img onerror> name renders inert.
KAN-151 | Planned | EP28 — Security Hardening |  | Must Have (pre-prod) | As the system, I want company HTML and logo uploads sanitized so a portal admin cannot inject active content to all employees. (F4) | header_html/footer_html sanitized on write (allowlist) or rendered as text (drop `
KAN-152 | Done | EP28 — Security Hardening |  | ✅ Done (app/config.py, run.py) | As the operator, I want secure runtime defaults so a misconfigured deploy fails safe. (F5) | App raises if SECRET_KEY unset outside dev; SESSION_COOKIE_SECURE/SAMESITE/HTTPONLY set; debug driven by env (default off); MAX_CONTENT_LENGTH caps request/upload size.
KAN-153 | Planned | EP28 — Security Hardening |  | Should Have | As the operator, I want required DB configuration with no personal defaults so missing config is caught, not masked. (F31) | app/config.py requires PGUSER/PGDATABASE (no 'samirroy' default); missing values raise a clear error at startup.
KAN-154 | Done | EP29 — Data Layer & Query Performance |  | ✅ Done… | As a user, I want dashboard/directory/analytics queries to use an index on employees.company_id so they don't seq-scan the whole table. (F6) | Composite (company_id, employment_status) index added (supersedes low-value idx_employees_status); EXPLAIN ANALYZE shows index usage on the directory + dashboard queries.
KAN-155 | Done | EP29 — Data Layer & Query Performance |  | ✅ Done (ADR-006 — app/db.py… | As the system, I want composite writes to be atomic so a mid-loop failure cannot leave partial data. (F8) | A transaction() context manager (single commit/rollback) is added and used by vacation-type create/edit and org-change apply; per-row-loop commits removed; failure rolls back the whole unit; read paths no longer sit idle-in-transaction.
KAN-156 | Planned | EP29 — Data Layer & Query Performance |  | Should Have | As a user, I want list/analytics pages to avoid N+1 queries so they stay fast as data grows. (F22) | Analytics overview replaces the per-feature COUNT loop with one GROUP BY route; vacation page computes used-days for all types in one GROUP BY; team-pending replaces the per-row correlated subselect with a single windowed/join query.
KAN-157 | Done | EP29 — Data Layer & Query Performance |  | ✅ Done (migration 07) | As the system, I want indexes on the org/vacation foreign keys that are filtered/joined so those scans use an index. (F23) | (company_id) indexes on business_units/locations/functional_units; idx on vacation_requests(vacation_type_id); confirmed via EXPLAIN.
KAN-158 | Planned | EP29 — Data Layer & Query Performance |  | Should Have | As a user, I want the employee directory paginated with a light list projection so a large company doesn't load everyone (with full skills/certs) at once. (F24) | Directory API paginates; a lightweight list query is separated from the detail query; skills/cert JSON_AGG only run for the detail view; serialization moved toward psycopg2 type adapters.
KAN-159 | Planned | EP30 — Scalability & Runtime |  | Must Have | As the operator, I want a DB connection pool so requests reuse connections instead of opening one each. (F7) | psycopg2.pool.ThreadedConnectionPool (or PgBouncer) sits behind get_db(); connection open-rate under load drops sharply; background threads draw from the pool.
KAN-160 | Planned | EP30 — Scalability & Runtime |  | Should Have | As a user, I want feature-access cached across requests so it isn't re-joined on every page render. (F16) | Short-TTL process cache keyed by (sorted(roles), company_id), invalidated on permission writes; per-request g cache retained; correctness preserved (SYSTEM_ADMIN bypass, company scoping).
KAN-161 | Planned | EP30 — Scalability & Runtime |  | Should Have | As the system, I want notification/pending counts pushed or combined rather than two polls per user every 60s. (F17) | Bell uses one endpoint returning both counts; polling is visibility-gated (or replaced with SSE/websocket); idle tabs stop querying.
KAN-162 | Planned | EP30 — Scalability & Runtime |  | Should Have | As the operator, I want uploaded logos in shared object storage so they survive across instances. (F18) | Logos stored in S3/GCS (or a shared volume) and served via signed URL/CDN; an upload on one instance is visible from another.
KAN-163 | Planned | EP30 — Scalability & Runtime |  | Should Have | As the system, I want bounded background workers so a spike or slow SMTP can't spawn unbounded threads/connections or lose work on restart. (F19) | Email + page-view logging go through a bounded worker pool / queue with backpressure and basic retry; work is not silently dropped on SIGTERM.
KAN-164 | Planned | EP30 — Scalability & Runtime |  | Could Have | As the system, I want only company_id in the session (not branding HTML) so the cookie can't overflow and branding can't go stale. (F25) | session['branding'] removed; branding loaded server-side via a cached lookup (pairs with KAN-160); cookie size bounded.
KAN-165 | Done | EP31 — Schema Source of Truth & Migrations |  | ✅ Done (database/schema.sql +… | As a developer, I want one authoritative schema so a fresh database matches production, including all currently-missing tables. (F9) | A single canonical schema (e.g. pg_dump --schema-only baseline or complete numbered migrations) recreates every live table — companies, employees.company_id, vacation_, page_views, user_notifications, org_change_, etc.; README bootstrap updated to use it.
KAN-166 | Planned | EP31 — Schema Source of Truth & Migrations |  | Should Have | As a developer, I want a migration tool with version tracking so applied migrations are recorded and ordered. (F9) | Alembic (or Flyway) adopted; existing migrations 02–06 folded into the tool; alembic upgrade head on a fresh DB yields the full schema.
KAN-167 | Planned | EP31 — Schema Source of Truth & Migrations |  | Should Have | As a developer, I want a single owner for feature/role seeding so setup_db.py and alter_table.sql can't diverge. (F9) | portal_features/role_feature_access DDL+seed defined once; the other path references it; onboarding a company is unambiguous.
KAN-168 | Planned | EP32 — Testing & CI Hardening |  | Must Have | As a developer, I want a real-DB integration test tier so SQL is executed against the actual schema. (F10) | Pytest tier spins up disposable Postgres (testcontainers or CI service container), applies schema+migrations, and exercises real routes/services; covers the org_change decide→apply flow asserting row state.
KAN-169 | Done | EP32 — Testing & CI Hardening |  | ✅ Done (.github/workflows/ci.yml —… | As a team, I want CI on every PR so a broken build/migration/test can't reach main. (F11) | GitHub Actions runs lint + full pytest + "build fresh DB from migrations then boot the app" smoke test; required status check; not bypassable like the local hook.
KAN-170 | Planned | EP32 — Testing & CI Hardening |  | Should Have | As a developer, I want coverage measured with a floor so thin/untested modules are visible. (F12) | pytest-cov added; --cov=app --cov-report=term-missing; CI fails under an agreed floor; email_service/page_tracker/skills_intelligence_service gaps surfaced.
KAN-171 | Planned | EP32 — Testing & CI Hardening |  | Should Have | As a developer, I want the mocked engine tests backed by behavior tests so they assert outcomes, not internal call order. (F10, testing #4) | The org_change (and vacation) approval flows have integration tests asserting final DB state; brittle SQL-substring/side_effect-ordering assertions supplemented rather than relied upon.
KAN-172 | Planned | EP33 — Frontend Modernization |  | Should Have | As a developer, I want shared JS in static/js/ ES modules so logic isn't copy-pasted across 7+ templates. (F26) | dom.js (escapeHtml + safe html\\ + el), avatar.js, format.js, api.js (postJSON/getJSON + CSRF header), modal.js created and loaded once; duplicated avatarColor/initials/esc/fmt removed from templates.
KAN-173 | Planned | EP33 — Frontend Modernization |  | Should Have | As the system, I want escaping to be the default path in the shared modules so new code can't reintroduce XSS. (F3) | All innerHTML builders use the shared safe helper; a lint/check or code-review note discourages raw innerHTML with interpolation.
KAN-174 | Planned | EP33 — Frontend Modernization |  | Should Have | As a keyboard/screen-reader user, I want to propose a position change without a mouse. (F20) | Org-tree cards expose a keyboard "Move…" affordance opening the same modal; aria-grabbed/live-region announcements; WCAG 2.1.1 satisfied for the flow.
KAN-175 | Planned | EP33 — Frontend Modernization |  | Should Have | As a screen-reader user, I want modals with proper dialog semantics so focus and context behave. (F21) | Shared modal.js adds role="dialog"+aria-modal, a focus trap, Esc-to-close, and labelledby; adopted by all modals.
KAN-176 | Planned | EP33 — Frontend Modernization |  | Could Have | As a developer, I want JS unit tests and cache-busted assets so client logic is verified and deploys don't serve stale files. (F27) | Vitest units on the pure helpers (avatar/format/escape); static assets get a build hash / ?v=; optional esbuild minify step.
KAN-177 | Planned | EP33 — Frontend Modernization |  | Could Have | As a maintainer, I want high-traffic inline styles moved to CSS classes and clickables made semantic so the UI is consistent and accessible. (F28) | Inline style= migrated to classes on the heaviest templates (start with admin/panel.html); non-semantic onclick divs replaced with <button>/<a> + type.
KAN-178 | Planned | EP34 — Architecture & Structure |  | Should Have | As a developer, I want a create_app(config) factory so the app can be built with test/staging/prod configs and isn't wired as an import side-effect. (F13) | create_app builds config, teardown, context processor, and route registration; run.py and tests use it; multiple app instances can coexist.
KAN-179 | Planned | EP34 — Architecture & Structure |  | Could Have | As a developer, I want route modules as Blueprints so there's no shared-singleton import cycle and areas can carry prefixes/error handlers. (F14) | Each route module is a Blueprint registered in the factory; route→route imports (e.g. company.py→admin.py) removed; shared helpers moved to services.
KAN-180 | Planned | EP34 — Architecture & Structure |  | Should Have | As a developer, I want pinned dependencies + a lockfile so builds are reproducible. (F15) | requirements.txt pins exact versions; a lockfile (pip-compile/uv) is committed; CI installs from the lock.
KAN-181 | Planned | EP34 — Architecture & Structure |  | Could Have | As a developer, I want helpers.py split and business logic out of routes so modules are cohesive and testable. (F29) | helpers.py split into services/{employees,org,vacation} + util/uploads; admin.py split by sub-area; routes act as thin controllers.
KAN-182 | Planned | EP34 — Architecture & Structure |  | Could Have | As a maintainer, I want a guard-decorator audit so authorization is consistent and documented. (F30) | Each @require_roles route reviewed; genuine feature pages converted to @require_feature_access; admin/config gates that stay role-based are documented (per CLAUDE.md, not blindly converted).
KAN-183 | Planned | EP38 — Employee Lifecycle Workflows |  | Should Have · P2 | As HR, I want an onboarding checklist workflow for a new hire so nothing is missed before day one. (EP38-S1) | Company-configurable task template (task, assignee by role or named person, due date relative to join_date); a checklist is instantiated when an employee is registered, and links back to that employee; each task carries status + who completed it and when; HR can see outstanding tasks per new hire and across the company before day one; new tables (KAN-166); company-scoped and gated by @require_feature_access.
KAN-184 | Planned | EP38 — Employee Lifecycle Workflows |  | Must Have · P2 | As HR, I want an offboarding workflow (access removal, exit date, asset return) so departures are clean and auditable. (EP38-S2) | Offboarding case sets employees.employment_status (RESIGNED/TERMINATED) and exit_date, and deactivates the portal user (users.is_active=false) — no route writes any of these today; asset-return / access-removal checklist completed before the case can close; the whole close-out is one atomic write (KAN-155); every step written to an audit trail that does not exist yet (D3); company-scoped and gated by @require_feature_access per CLAUDE.md; non-ACTIVE employees verified to drop out of directory, dashboard, org tree, search and manager resolution — reports of an offboarded manager must not be orphaned; GDPR retention/erasure per the BA's criteria file.
KAN-185 | Done | EP38 — Employee Lifecycle Workflows |  | Should Have · P2 — 🟡 In progress.… | As a manager/HR, I want a transfer flow (BU / functional unit / location / manager) reusing the org-change engine so moves are consistent. (EP38-S3) | Transfers are raised as org_change requests and run through the existing sequential multi-level approval engine (app/services/org_change_service.py) — reused, not re-implemented; no bypass path; the KAN-139 rule stands (an employee can never initiate their own move); nothing is applied until the final level approves and any rejection applies nothing; company-scoped; the apply step is atomic (KAN-155).
KAN-186 | Planned | EP38 — Employee Lifecycle Workflows |  | Could Have · P3 — ⏸ Later (roadmap §E… | As HR, I want rehire to restore/relink a prior employee record so history isn't lost. (EP38-S4) | Registration detects an existing prior record for the same person and offers relink instead of creating a duplicate; the record is re-activated with a new employment period distinguishable from the old (prior exit_date preserved, not overwritten); prior org, manager, skills and certification history retained; the audit trail spans both periods.
KAN-187 | Done | EP38 — Employee Lifecycle Workflows |  | Must Have · P1 — ✅ Done (read UI is… | As a compliance owner, I want one immutable, company-scoped audit trail so any change to a person's record can be explained after the fact. (D3 — platform capability, prerequisite for KAN-184) | audit_log table + app/services/audit_service.py; append-only enforced by a DB trigger on UPDATE (DELETE deliberately left open for retention purge — TD-13); JSONB field-level diffs only, never whole rows; subject recorded as employee id + employee number, never name, so a row survives erasure; mandatory non-null company_id taken from the affected entity; closed action enumeration; mandatory reason; correlation id grouping one unit of work; outcome + error code; retention_class. record() joins the caller's open transaction() (KAN-155) and never opens its own — the audit row commits with the change and vanishes with a rollback. Reversible migration 08_audit_log(_down).sql + regenerated…
KAN-188 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W0 — platform enablers and two debts (stage S2) · KAN-208 moved out… | Must · P1 | As the product owner, I want to expose or hide a feature for one company without hiding it for another, and have that honoured everywhere, so I can package the product per tenant. | company_features.is_enabled becomes a term in the single central resolution (_load_feature_access), one added LEFT JOIN on the query that already runs — effective access = tenant switch AND role grant. The default for an absent row is a portal_features.default_enabled column, not a Python constant. A repair-then-materialise migration: repair the 14 rows that are FALSE for features nothing consults (excluding reports and skills_intelligence, whose values are live), then materialise a row for every (company, feature) pair. The acceptance criterion is a 330-cell before/after matrix — 3 companies × 11 features × 10 roles resolve identically after the migration — captured as a fixture before…
KAN-189 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W0 — platform enablers and two debts (stage S2) · KAN-208 moved out… | Must · P1 | As HR, I want a position change to carry the date it takes effect, so placement and pay move on the same day and history is not fudged. (D4d · resolves CFL-4 · unblocks AC-185-07 on KAN-185) | effective_date on org_change_requests and create_request(); rendered in the shared move modal (deliberately absent today rather than silently discarded); _apply_change uses it as the boundary for closing the outgoing assignment and opening the incoming one. Half-open [from, to) intervals adopted project-wide (ADR-020), which closes CFL-4's one-day overlap with no history rewritten. After any applied change: exactly one current assignment, no overlapping day, asserted by direct DB query. Also fixes DEF-42-2 — _apply_change closes manager_relationships rows with no effective_to and the dev DB holds 2 such rows; the pattern EP42 was told to copy is undated on the closing side.…
KAN-190 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W1 — job architecture (stage S3) — R6 · a complete slice with no… | Must · P1 | As a customer admin, I want to define my own job families, levels and steps — each step with its own responsibilities and expectations — so the ladder matches how we actually organise work and people can read what each… | Company-scoped job families; ordinal levels within a family, each carrying its own title. Steps run from .0 (entry) upward: a level's configured step_count is the number of increments above entry, so step_count = 5 yields six discrete values .0 … .5 — matching the owner's own 2.0 … 2.5 example. Configured per level, per company, with no default — Trainee→Junior and Junior→Mid are genuinely different distances; range 1–12 as a sanity bound, and the configurator requires an answer rather than defaulting one. Each step carries an authored description of its responsibilities and expectations (A1's largest addition) — readable by every employee, because that is its purpose. Registers the fourth…
KAN-191 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W1 — job architecture (stage S3) — R6 · a complete slice with no… | Must · P1 | As HR, I want every existing employee placed on a level, so the ladder has people on it. (R6 · R2 · D7 · A1 · re-scoped by CFL-42-41) | Effective-dated assignment of an employee to a (family, level). A mapping screen listing every distinct free-text job_title with its headcount, assign a level per title, bulk-apply, plus a CSV round-trip — this screen decides whether the backfill finishes. Step fitting is deliberately NOT in this story — it moved to KAN-209 in W2, because fitting a step to pay needs both KAN-206's pay points and actual pay data from KAN-193/195, and neither exists in W1 (CFL-42-41 — the original build order would have run the fitted backfill a wave before the thing it fits against, producing exactly the .0-for-everyone alert storm the fitting exists to prevent). Everyone therefore defaults to step .0 here,…
KAN-192 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W3 — coupling to the workflows (stage S3) — R3, R4 | Must · P1 | As a manager or HR admin, I want step advancement to be an explicit recorded decision taken at a review, which proposes the matching pay adjustment rather than applying it. (R6 · D3.4 · A1 — OQ-1 CLOSED: confirmed not… | Step advancement is an explicit audited action carrying a mandatory review_context — PROBATION_REVIEW · MID_TERM_GOAL_REVIEW · PERFORMANCE_REVIEW · OFF_CYCLE — plus a review date and optional note. Mandatory to answer, with an off-cycle option, mirroring D4c: an unanswered context means the question fell on the floor. EP42 records that a step change happened at a review; it does not build the review — no cycles, no scheduling, no reminders, no goals, no ratings, no calibration, no probation entity. Advancing a step pre-fills a COMPENSATION_REVIEW at the new step's pay point and routes it through the existing chain — it never applies a pay change. Four reasons converge: A1 makes progression…
KAN-193 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As HR, I want the product to hold an effective-dated salary for an employee, so pay is a governed record rather than a spreadsheet. (R1 — the spine of the epic) | Append-only, effective-dated compensation history: amount (NUMERIC(14,2), exact decimal, major unit, > 0), ISO-4217 currency (always explicit, never defaulted), FTE (0.01–1.00, mandatory and defaultless for PART_TIME), pay basis (ANNUAL/MONTHLY/HOURLY), effective_from, actor, mandatory reason, correlation id. No UPDATE and no DELETE path — a correction is a new record, a void is a marked record (compensation:d). "Current" is computed, never stored — a stored is_current on a future-dated row would need a scheduler that does not exist. Half-open intervals with a GiST non-overlap constraint; a same-date correction is permitted and tie-broken by created_at with the superseded row marked, so…
KAN-194 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As an employee, manager and HR admin, I want to see exactly the pay I am entitled to see and nothing else, so the most sensitive data in the product is safe by default. | Three feature codes registered in all four places — compensation, compensation_self, pay_equity. The default matrix as a ceiling a tenant may widen or narrow with no extra checks in any route: manager sees direct reports only, not the subtree; department and location heads nothing by default; COMPANY_ADMIN nothing by default; employees see their own via compensation_self. Row scoping lives in the service layer and is documented as not the forbidden sub-flag — the flag says whether you reach the surface, the scope says which rows it returns, which is what company scoping already does everywhere. "My Pay" server-scoped to session.employee_id, never from a parameter. r/w/d separable; a w-less…
KAN-195 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As HR, I want to load our existing salaries in bulk and fix individual rows by hand, so we can get to usable coverage in days rather than a quarter. (R2 · D7) | CSV import with dry-run → diff → commit, reusing the EP35-S2 surface, never a second importer; the amount column is named amount (not annual_base, which would hold a monthly figure and produce a first import wrong by a factor of twelve); row-level errors reported with reasons — it must not inherit DEF-42-1's silent-SKIPPED pattern; a file that would write null or zero over an existing salary is rejected at preview; atomic per batch. Single-employee manual entry gated compensation:w, with a mandatory reason category from a seeded, company-editable list (Annual review, Promotion, Market adjustment, Role change, Correction, Other) plus optional free text. "No salary recorded" and "Not…
KAN-196 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W3 — coupling to the workflows (stage S3) — R3, R4 | Must · P1 | As a manager or HR admin, I want a position change to carry its pay decision through the same approval, so a move is never applied with the pay question unanswered. | The compensation block lives inside the shared _move_modal.html. The pay decision is mandatory to answer, not mandatory to change — No change · New salary · Defer (reason required), nothing pre-selected. A money-bearing request is refused at create time if any chain step has no approver holding compensation:r (using KAN-188's non-session resolver), naming the step and writing nothing. A manager without compensation:r cannot route around the control: their request records NOT_ANSWERED_NO_PERMISSION and the first compensation:r approver must answer before approving — the question is always answered before apply, and the manager still sees no pay. The apply never writes null or zero over an…
KAN-197 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W3 — coupling to the workflows (stage S3) — R3, R4 | Must · P1 | As HR, I want a level change to be a first-class request with a salary review that cannot be skipped, so a promotion never quietly happens without a pay decision. (R4 · closes backlog open items #3 and #4) | request_type ∈ TRANSFER · LEVEL_CHANGE · COMPENSATION_REVIEW, every existing row defaulting to TRANSFER. Named LEVEL_CHANGE, not PROMOTION, with a stored direction of UP/DOWN/LATERAL — D3 permits downward and sideways moves, and a display label cannot fix an audit trail that says PROMOTION_APPLIED for a demotion. "Promotion" remains the word shown to users when the direction is UP, which is what R4 asked for. All three types run on the existing engine and chain — no second engine. A LEVEL_CHANGE proposes a new (family, level, step) and may also change placement; "no change" on an upward move requires an explicit recorded reason. A company may configure a different chain per type, falling…
KAN-198 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W3 — coupling to the workflows (stage S3) — R3, R4 | Must · P1 | As a compliance owner, I want two different people required on any approval that moves money, so a two-level control is not one person twice. | For any request carrying a compensation or level change: a user who has decided one level cannot decide another on the same request; the initiator may not decide any level (without this, an HR_ADMIN who also holds PORTAL_ADMIN raises a pay rise and satisfies level 1 by role — the control passing while doing nothing); not configurable, not overridable, and not bypassable by SYSTEM_ADMIN — a control with a hole exactly where the demo identity sits is not a control. A money-bearing request requires ≥2 independently satisfiable levels and is refused at create time otherwise — and this is not an enhancement, it is the difference between KAN-198 existing and KAN-198 working. Evidence (Architect…
KAN-199 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As a customer admin, I want to say which locations share a pay market, so people are only compared against the market they are paid in. | A pay market is a company-defined grouping of locations, defaulting to one per locations.country. It is part of the comparison group key and therefore a hard prerequisite of KAN-200, and it is the object the step pay points in KAN-206 attach to. Carries the annualisation constants — monthly_payments_per_year (12–14) and standard_annual_hours — on the pay market, not the company: Acme's Porto office (Portugal, 14 statutory monthly payments) sits in the same company as Hamburg and Tallinn (12), and a company-level constant understates every Porto salary by ~17%, which is more than three times the 5% threshold the feature is built around. A merged multi-currency market is refused unless an…
KAN-200 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W4 — pay equity (stage S3) — R5 | Must · P1 | As HR, I want the system to tell me where somebody's pay does not match the step they are on, so I find it before they or a regulator does. (R5 · D1 re-ruled by A1) | Check A′ — step-pay correspondence. Absolute, not statistical. The reference is the employee's own step's configured pay point (KAN-206), not a group median and not a band midpoint. No minimum group size — n = 1 is a valid, meaningful check. No coverage gate. Two finding types with asymmetric severity, because the owner's stated concern is directional: PAY_BELOW_STEP is primary ("they took the responsibility, the pay never followed") and PAY_ABOVE_STEP is secondary, lower severity, different copy — it is legitimate far more often than not (market premium, red-circled legacy pay), and weighting them equally fills the queue with things nobody should act on. Flag when the employee's pay is…
KAN-201 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W4 — pay equity (stage S3) — R5 | Must · P1 | As the pay-equity responsible, I want each finding to reach me, stay in one place until I have dealt with it, and then go away, so the queue is worth working. | Three finding types with distinct copy, severity and disposition categories — PAY_BELOW_STEP (primary) · PAY_ABOVE_STEP (secondary and SILENT — register only, no bell entry, no badge) · GENDER_GAP. Silent is a legitimate expression of "lower severity" when the alternative feeds R-1: a notification whose honest review outcome is "nothing to do" is how a channel gets muted, and this channel is shared with the primary check; raising one pay point creates dozens of PAY_ABOVE_STEP at once (CFL-42-48). reference_value and deviation_pct render only to holders of both pay_equity:r and compensation:r — reference_value × (1 + deviation/100) is the subject's salary, so a stored column inherits…
KAN-202 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W4 — pay equity (stage S3) — R5 | Should · P2 | As HR or a compliance owner, I want to see how someone's pay and their step got to where they are, without pay amounts leaking into the audit trail. (D5.6 · A1) | A per-employee compensation timeline (effective date, amount, currency, FTE, level/step, actor, reason), shown alongside the step and roadmap timeline — "how did this person get here" is one story, not two, and after A1 the step history is what explains the pay history. Gated compensation:r and row-scoped, joined to audit_log by correlation_id so the two read as one story. audit_log diffs carry no amounts — has_change, direction, pct_change_band (half-open buckets on the absolute percentage), currency, effective_date, level/step before→after only — enforced by a per-action closed diff-key allowlist, which is stronger than guessing key names. The guarantee is scoped honestly: it covers…
KAN-203 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W0 — platform enablers and two debts (stage S2) · KAN-208 moved out… | Must · P0 — Critical, pre-existing,… | As a compliance owner, I want it to be impossible to raise or approve a request about myself, so nobody can be on both sides of their own move or their own pay. | Subject ≠ initiator: _can_initiate_for refuses when the subject is the initiator, for every request type and every role including HR_ADMIN, PORTAL_ADMIN and SYSTEM_ADMIN — the admin exemption exists so HR can move other people, and it has never been intended to cover acting on oneself. Subject ≠ decider: decide() refuses when the decider is req['employee_id'], at any level, for any role. Both refusals are specific, audited and covered by regression tests that fail without the guard. CLAUDE.md's org-change invariant 2 is reworded in the same commit to say explicitly that nobody, including admins, may initiate or decide a request whose subject is themselves. Universal — not money-scoped; the…
KAN-204 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W0 — platform enablers and two debts (stage S2) · KAN-208 moved out… | Must · P1 | As any user, I want the shared shell to give a visible focus ring, announce async changes and respect reduced motion, so every new screen is usable without inventing its own. (EP33 debt, delivered here because EP42… | Three shared additions to the shell: A1 a global :focus-visible indicator (today only .row-menu-btn and .row-menu-list > * have one); A3 shared live regions in base.html (today the only live region in the product is private to _move_modal.html); A9 a prefers-reduced-motion block (today absent). EP42's coverage meters, progress bars and equity spinner all animate. No EP42 screen starts before this lands. Tagged EP33 so that epic's scope shrinks honestly rather than EP42 absorbing it invisibly.
KAN-206 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As a customer admin, I want to say what a step is worth, so pay can be checked against the step somebody is actually on — and computed when they move. | Per (job level × pay market): a base pay point (the rate at entry, step .0) and a step increment — the company-defined percentage the owner meant by "5%". Increment configured per level with an optional per-step override. Compounding: each step's pay point is the previous step's uplifted by the increment — compound, not linear. His phrasing describes the gap between consecutive steps, and the rationale is an adjustment to that person's pay. Across a 5-step level at 5% the two readings differ by ~2.1% of salary — small enough that engineering would guess either way and never notice, large enough to be wrong, so it is ruled rather than inferred. Arithmetic per BR-1.5 (exact decimal, no…
KAN-207 | Done | EP42 — Compensation, Job Architecture & Pay Equity | W1 — job architecture (stage S3) — R6 · a complete slice with no… | Must · P1 | As an employee, I want to read what my next step requires of me — written for me by my manager — so I know what I need to do next. As a manager, I want to author it. (A1 — the object the owner actually asked for) | Distinct from KAN-190's generic step expectation: the expectation says what step 1.2 means here; the roadmap says what you, specifically, need to do to get there. Authored by the subject's solid-line manager — who must be seeded job_architecture:w, row-scoped to their direct reports (CFL-42-35: the fourth code was created so a manager could author a roadmap, and the seed as first written gave them no w at all, blocking this story outright) — or by any other job_architecture:w holder. The employee is notified once, in-app, when a roadmap is written for them (overruling the BA's and UX's "no": a roadmap the employee does not know exists delivers exactly zero transparency, and "it appears on…
KAN-208 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | Conditional slice — the gender pay-gap check (Check B) — ⬜ not… | Conditional · P3 — nothing depends on it | As UAT and anyone demoing this, I want the seeded population to carry gender values, so the gender pay-gap check has data to run on. (A1 §4 — owner-authorised) | employees.gender is NULL for 100% of the seeded population (DEF-42-3), so Check B would report "insufficient gender representation" for every group in every tenant and could not be demoed at all. Assign values across the seeded population in the seed files and a migration — a dev DB updated by hand while seed_data.sql / telia_seed.sql stay unchanged is exactly the DEF-004 trap that broke CI on 9 Aug. Deterministic and reproducible, not per-row random, and shaped so at least two comparison groups satisfy Check B's minimums (n ≥ 5 with ≥ 2 of each gender) — an assignment that leaves the check undemonstrable has not done its job. OTHER is present in the population, because the…
KAN-209 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As HR, I want to reconcile what people are actually paid against what their step is worth, decide each difference once, and only then let the fairness check run. (A6 §2 — replaces the forbidden step-fitting backfill ·… | ⛔ The previous content of this story — "fits the step to the pay, not the pay to the step" — is FORBIDDEN by A6 and is withdrawn in full. Fitting a step from a salary is the model the owner rejected. The step now comes from the job, assessed by the employee's manager in KAN-191 (W1). This story handles the other half — and it has to solve the day-one alert storm that fitting used to hide. For every assessed employee, compare recorded base with the step's value as at the reconciliation date, and require one recorded disposition each before Check A″ may run for that company. It opens with the totals, not a list, because the HR director's first question is "what does adopting this ladder cost…
KAN-210 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As a customer admin, I want to move the whole ladder's pay rates when the market moves, so the pay-fairness check does not start flagging everybody the first time we grant a raise. | Re-base: raise every pay point for a job family or a pay market by X%, effective on a date, with a mandatory reason, in one audited transaction. This is the half of the annual hike cycle that stays in EP42, and it is why EP42 is safe to ship whether or not EP43 follows. Without it, an ordinary hike makes the equity register unusable in a single cycle — with a 5% increment, any hike above 2.5% puts every employee nearer the next step's pay point than their own, so a 4% hike flags the entire workforce as PAY_ABOVE_STEP (4.00% from their own point, 0.95% from the next). This corrects A2's own premise that the drift is "silent": under the nearest-step rule it is loud, and it arrives in cycle…
KAN-211 | Planned | EP43 — Annual Compensation Review Cycle |  | Must · P2 | As a customer admin, I want to open an annual compensation cycle for a year, so pay reviews happen as a governed round instead of ad hoc. | A cycle is per company, per year, with a name, an effective date and a lifecycle DRAFT → OPEN → APPROVED → APPLIED → CLOSED. One open cycle at a time per company. Company-scoped, audited at every transition, gated on the compensation feature codes. Reuses EP42's effective-dating convention (ADR-020, half-open).
KAN-213 | Planned | EP43 — Annual Compensation Review Cycle |  | Must · P2 | As a manager, I want to distribute the cycle across my team, so the people who took on most get most. | Per-employee proposals generated from current base × (1 + guideline × band multiplier); a manager worksheet showing a running total against the budget, over-budget warned and reasoned, never blocked (invariant 3). Row-scoped exactly as pay is — a manager proposes for their direct reports and sees nobody else's numbers. ⚠ A6 — re-specified. This is no longer a percentage-distribution round. Under A6 pay moves for exactly three reasons — the step moved (at that transition's rate), the ladder moved, or an exception was attributed as additional pay — and a discretionary per-person percentage is none of them. The worksheet becomes a step-movement and additional-pay round: the manager proposes…
KAN-214 | Planned | EP43 — Annual Compensation Review Cycle |  | Must · P2 | As HR, I want to approve the cycle once and have it apply, so 500 pay changes do not need 500 approvals. | One cycle-level approval satisfying invariant 1 — two different people, the initiator excluded — then an atomic bulk apply on the effective date, each employee getting a normal EP42 compensation record so the timeline and the equity check see it as ordinary pay history. One correlated audit set with counts (invariant 2). Partial application is not a state that can exist.
KAN-215 | Planned | EP43 — Annual Compensation Review Cycle |  | Must · P2 | As a customer admin, I want closing the cycle to move the ladder too, so the fairness check still means something next year. | Close-out re-bases the ladder by the market component, using KAN-210's capability, on the same effective date. Without this the check flags the whole workforce in the first cycle (CFL-42-54). Cycle history is retained and readable; a finding raised before the re-base still explains itself against the pay point in effect at its evaluation date.
KAN-216 | Planned | EP43 — Annual Compensation Review Cycle |  | Must · P2 | As a customer admin, I want to define what our performance bands are and what each is worth, so the hike policy is ours and defensible. | Company-defined ordinal bands (e.g. below / meets / exceeds / outstanding), each mapping to a configured multiplier on the cycle guideline. Authored on an admin page by the employer, per company. Nothing predetermined and nothing suggested — no shipped band set, no shipped multipliers, no "typical is 3–5%" helper text, no placeholder. A company that has not authored a policy cannot open a cycle. Versioned, auditable, and inspectable without exposing any individual's data — because performance-related pay is works-council territory in Germany and the Nordics (where the seed data lives), and a works council may need to review and agree the bands before the cycle operates. That promotes OQ-8…
KAN-218 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | W2 — pay policy, the compensation record, additional pay, and the… | Must · P1 | As local HR, I want to record money an employee receives outside the ladder, with a reason, so a retention save does not corrupt the ladder. (A6 §3 — the owner's own mechanism) | Base pay and additional pay are two distinct, separately-governed amounts. Base is governed by the step and moves only when the step moves or the ladder moves; additional pay is a human decision for a named reason, outside the ladder. His example: Tom is at 2.1 on €51,000 and about to resign; local HR grants 5%. Tom stays at step 2.1, base stays €51,000, and €2,550 is recorded as additional pay with a reason. Total cash €53,550, and the correspondence check raises nothing — "that does not mean he will be assigned to 2.4 or 2.3 just to match the salary." Mandatory reason code from a seeded, company-editable list (Retention · Market premium · Red-circled legacy pay · Temporary responsibility…
KAN-219 | Done | EP44 — Performance Management |  | Must · P2 | As a customer admin, I want to open a review cycle for a period, so performance conversations happen as a governed round rather than ad hoc. | A cycle is per company, per period, with a name, a window and a lifecycle DRAFT → OPEN → IN_REVIEW → CALIBRATION → CLOSED. One open cycle at a time per company. Registers the EP44 feature codes in all four places (setup_db.py, a migration, seed_rbac.sql, and default role_feature_access rows in both) — the DEF-004 rule. Company-scoped, audited at every transition, half-open effective dating per ADR-020. Nothing about the cycle's content is predetermined: the product ships no scale, no form, no rubric and no schedule.
KAN-220 | Done | EP44 — Performance Management |  | Must · P2 | As HR, I want the cycle to know who is in it, so joiners, leavers and probationers are handled deliberately rather than by accident. | Eligibility per cycle: joiners after the window opens, leavers before it closes, part-cycle participants, employees with no manager, and CONTRACTOR/INTERN handling. Every exclusion is counted and shown with its reason, never silent — the same rule as compensation coverage. Company-scoped.
KAN-221 | Planned | EP44 — Performance Management |  | Must · P2 | As an employee and my manager, I want to agree what I am working towards this period, so the review has something concrete behind it. | ⚠ A7: goals carry a type — BUSINESS or DEVELOPMENT — rendered as two named sections, not a tag; both are agreed with the employee at the start of the year and the agreement is recorded. Goal/objective authoring by employee and manager, per cycle, versioned. Optional cascade from a parent goal — cascade is a link, never an automatic copy or an enforced target. Row-scoped: a manager sees their direct reports' goals and nobody else's. Audited.
KAN-222 | Planned | EP44 — Performance Management |  | Must · P2 | As an employee, I want to record progress and check-ins during the period, so the review is not a memory test. | ⚠ A7 — reframed as MILESTONES ACHIEVED: dated, authored by the employee, against a specific goal, visible to the manager, added throughout the year. Not approved one by one — a year-long approval queue is how this dies; the manager weighs them at review time. Narrative check-ins against a goal, timestamped, authored by either party, visible to both. No score, no percentage complete, no RAG, no automatic status. A completion percentage is a rating with a friendlier name and it is refused.
KAN-223 | Planned | EP44 — Performance Management |  | Should · P3 | As a customer admin, I want a library of goal templates we wrote ourselves, so managers are not starting from a blank page. | Company-authored templates, versioned. Nothing predetermined and nothing suggested — the product ships no example goals and no "typical" text (A3-1's discipline, extended: a suggested goal is a recommendation about somebody's job we have no basis for).
KAN-224 | Planned | EP44 — Performance Management |  | Must · P2 | As an employee, I want to write my own assessment before my manager writes theirs, so my view is on the record. | ⚠ A7 + OQ-10: the employee submits a narrative AND their own rating, and that submission GATES the manager's rating (not merely its visibility). The cycle carries a self-assessment deadline; after it HR — never the manager — may record SELF_ASSESSMENT_NOT_SUBMITTED, the employee is notified, and the manager may proceed. "Did not submit" and "submitted with nothing in it" must never render the same — one is an absence, the other a statement. A late submission is accepted and does not erase the fact. Self-assessment per cycle against the company's form. Visible to the manager on submission; the manager's assessment is not visible to the employee until the cycle reaches its release point, so…
KAN-225 | Planned | EP44 — Performance Management |  | Must · P2 | As a manager, I want to assess each of my people against what we agreed, so the conversation is prepared and recorded. | ⚠ A7 + OQ-11: per goal an outcome — ACHIEVED · PARTIALLY_ACHIEVED · NOT_ACHIEVED — plus a comment; then an overall rating. The overall rating is NEVER computed from the per-goal outcomes and no suggested rating may appear on the screen — a suggestion is a computed decision with a human rubber-stamping it. Blocked until the employee has submitted or HR has recorded not-submitted, and the block says which. Manager assessment per employee per cycle, row-scoped to direct reports. Cites the goals from KAN-221 and, where one exists, the step roadmap from EP42's KAN-207 — the owner's own narrative link ("the expectation from the employee is if they satisfy in next level the compensation review…
KAN-226 | Planned | EP44 — Performance Management |  | Must · P2 | As a customer admin, I want to define our rating scale, so the words mean what we mean by them. | ⚠ A7 — the owner's four labels ship as the DEFAULT scale: Below expectation · Meeting expectation · Above expectation · Beyond expectation. Still configurable and versioned as below. Company-defined ordinal scale with authored labels and descriptions, versioned — a rating from 2027 must still be readable in 2029 against the scale that produced it. Nothing predetermined, nothing suggested: no shipped scale, no default point count, no "typical" wording. A company that has not authored a scale cannot open a cycle.
KAN-227 | Planned | EP44 — Performance Management |  | Must · P2 | As a customer admin, I want to define the review form, so it asks what we ask. | Company-authored sections and questions, versioned per cycle. Free-text, scale and goal-linked question types. No scoring arithmetic across questions — a weighted total is a computed rating, which is the thing KAN-232 gates.
KAN-228 | Planned | EP44 — Performance Management |  | Must · P2 | As an employee, I want the review conversation recorded honestly, so the record says what actually happened. | The conversation is recorded with a date and both parties. The employee confirms the conversation happened; they do not "accept" a rating — the button reads Confirm we discussed this, never Accept, and the displayed state is Discussed with Ravi on 14 March, never "agreed" (standing rule 6 — a label is a claim; recording "agreed" when somebody merely read it is a false record about a person). A right of reply is mandatory, not optional (KAN-234). Non-acknowledgement blocks nothing and is surfaced back to the manager.
KAN-229 | Planned | EP44 — Performance Management |  | Must · P2 | As HR, I want a calibration session where managers compare their assessments, so ratings mean the same thing across teams. | A calibration session is a human forum: a named group of employees, a named set of participants, a scheduled moment, and a record. Participants see the group's assessments side by side, row-scoped to the session's population. The system convenes and records; it never proposes, orders or adjusts. Audited.
KAN-230 | Planned | EP44 — Performance Management |  | Must · P2 | As HR, I want to see the shape of our ratings during calibration, so a session can see its own bias. | The distribution across the session's population is shown — counts per scale point, and a comparison against the company's other sessions. Never enforced. There is no target curve, no quota, no warning that a distribution is "wrong", and no configuration option that would create one: a configurable forced curve is an automated decision with significant effect wearing a settings page, and it is refused at the product level rather than left to a tenant. No aggregate rendered below n = 5 (CFL-42-32 applies here exactly as it does to pay).
KAN-231 | Planned | EP44 — Performance Management |  | Must · P2 | As a compliance owner, I want every rating that calibration changed to say who changed it and why, so a decision about a person can be explained. | Every change to a rating inside calibration writes actor, reason (mandatory), before → after, and the session it happened in. The employee's own view (KAN-234) shows that a calibration adjustment occurred — hiding it would make the record dishonest, which is the same reasoning that gives the subject of a pay-equity finding read access without disposition controls. Append-only; no silent overwrite.
KAN-232 | Planned | EP44 — Performance Management |  | Must · P1 | As a compliance owner, I want the Art. 22 / EU AI Act gate built into the review rather than assessed after it, so we do not cross the line by increment. | Human-in-the-loop attestation on every rating that reaches a pay consequence: a named human confirms the decision, and the confirmation is the record. An explainability record per rating — the goals, the assessments and any calibration change that produced it, retrievable as one narrative for the subject. A hard product rule, asserted by test: no ranking, score, index or model output is computed by the system and applied to a person. No automated decision-making, no profiling, no algorithmic ranking anywhere in EP44. The gate engages — and the story does not enter the backlog until it has full high-risk treatment — the moment anyone proposes a suggested rating, a ranked list, a forced…
KAN-233 | Planned | EP44 — Performance Management |  | Must · P2 | As HR, I want ratings history, and I want it visible only to the people entitled to it. | Ratings history per employee per cycle, retained and readable against the scale version that produced it. Its own feature code, row-scoped like pay, with its own negative-visibility suite asserting absence from the payload and not merely from the DOM — absent from the profile, the directory, the org tree, search, every export and every other feature's surface. Cross-tenant subject ids return 404, not 403 (CFL-42-33's ruling, applied here from the start rather than retro-fitted).
KAN-234 | Planned | EP44 — Performance Management |  | Must · P2 | As an employee, I want to read my own review and say something back, so the record is not only my manager's version. | The employee sees their own assessment, their rating, and the fact of any calibration adjustment, after the cycle's release point and not before. A right of reply, recorded alongside and never editable by the manager. Plain language, no jargon, no forward-looking language that reads as a promise — the same discipline as "My Pay" and the top-step signal.
KAN-235 | Planned | EP44 — Performance Management |  | Must · P2 | As HR, I want the rating to feed the pay decision and nothing else, so a performance judgement does not leak into every other surface. (the pay seam — EP43's KAN-216 reads this) | Single-purpose, enforced the way pay is: written in a cycle, read by the pay cycle that consumes it, used for nothing else. Absent from the profile, the directory, the org tree, reporting and every export. Row-scoped, its own gate, its own negative-visibility assertions. Blocked by KAN-232 — no rating reaches a pay consequence before the Art. 22 gate is in place. Not shown to the employee as a pay input — communicating a pay decision is a conversation, and the rating's route to money is EP43's, not a screen here.
KAN-236 | Planned | EP44 — Performance Management |  | Must · P2 | As a manager, I want a review to be the moment a step change is recorded, so EP42's review_context points at something real. | A closed review cycle becomes a selectable review_context for EP42's KAN-192 step change, with its date. The pay proposal that follows cites the roadmap it fulfils (EP42's KAN-207) — A2's narrative link, finally connected to a real review instead of a free-text context. This does not make a step change automatic and it does not make a review required for one: OQ-1 is closed — progression is a human decision — and the off-cycle context stays. And it does not weaken A6: the review justifies the step, the step determines the base pay, and nothing here lets a rating set an amount.
KAN-237 | Planned | EP44 — Performance Management |  | Should · P3 | As HR leadership, I want to know whether the cycle is actually happening, without seeing who scored what. | Completion and cycle-health reporting only — assessments submitted, conversations recorded, calibration sessions held, overdue counts. No individual ratings, and no aggregate of any kind below n = 5 (CFL-42-32). Company-scoped; cross-tenant aggregation of any kind is refused, including for SYSTEM_ADMIN.
KAN-238 | Planned | EP44 — Performance Management |  | Must · P2 | As a works-council representative or compliance owner, I want to review the rules before they are applied to people, so consultation is possible. | The policy — the rating scale (KAN-226), the review forms (KAN-227), the calibration rules (KAN-229/230) and the rating-to-pay mapping (EP43's KAN-216) — is versioned, auditable and inspectable without exposing any individual's data. A named reviewer can read the whole policy for a period and see nothing about any person. A launch blocker for the German and Nordic markets, not a build blocker, and it goes on the Customer-Readiness checklist. Note the standing platform limitation (CFL-42-22): the access model still cannot express "read company-wide, write nothing", so a read-only reviewer has no clean grant. This is the second epic to need it — if OQ-8 comes back "yes", that limitation…
KAN-239 | Planned | EP44 — Performance Management |  | Must · P2 | As a DPO, I want to know what performance data we keep, for how long, and what erasure does to it. | Retention class and period for assessments, ratings, calibration records and check-ins, per company, reusing EP38's single retention clock (one clock, not a second one — OQ-BA-6's ruling). What erasure removes and what must survive, extending the BA's §4.7 enumeration the way CFL-42-3 extended it for pay — and the same lesson applies: EP38's erasure list predates this data class and will be false the day EP44 lands. DPIA items routed to the DPO list alongside DPO-1. Nothing here is legal advice.
KAN-240 | Planned | EP44 — Performance Management |  | Should · P3 | As a compliance owner, I want to know whether our ratings are biased, so we can look at it rather than assume. | Measure the rating distribution across the protected characteristics the tenant lawfully holds, per cycle, per level. Report only — never auto-correct, never adjust a rating, never suggest one. No aggregate below n = 5. Blocked on the same purpose-limitation question as EP42's DPO-1: holding a characteristic for one purpose does not make it lawful to process for this one. Runs after KAN-232, and it is a measurement, not a compliance conclusion — the same framing rule every pay-equity screen carries.
KAN-241 | Planned | EP42 — Compensation, Job Architecture & Pay Equity | KAN-241 — NEW STORY: the readiness outcome | Must · P1 | As a manager and employee, I want the review to conclude with where this person stands on the ladder, so the outcome is stated rather than left implied. | A fixed three-value outcome, deliberately NOT company-configurable: FOCUS_ON_CURRENT_ROLE · READY_IN_12_24_MONTHS · READY_FOR_NEXT_LEVEL. Fixed because unlike the rating scale — which is about a period's work and is properly a company's own vocabulary — these three are structurally tied to the product's own promotion mechanism (stay / progressing / level change), and a tenant renaming them would break the link to KAN-197. Recorded as the conclusion of the discussion, not before it: it is an outcome of a conversation, which is what the owner described. READY_FOR_NEXT_LEVEL NEVER auto-creates anything. It is a stated view that a human then acts on by raising a level change through the…

## Delivered
Delivered
Only stories with a recorded evidence row. If it is not here, it has not been evidenced.
ID | Date | Test evidence | Caveats? | What landed
KAN-188 | 10 Aug 2026 | pytest 4,727 · browser 105/105 · vacation 39/39 | YES — see notes | Effective access is now tenant switch AND role grant, resolved by one added LEFT JOIN on the query _load_feature_access() already ran. The two hand-rolled tenant switches (_analytics_enabled, _si_enabled) are deleted, and a grep-assert fails the build if company_features is read outside the resolver and the toggle route. feature_access_for(user_id, company_id) delivered for KAN-196, deliberately uncached (it answers about somebody else). Every toggle audited as COMPANY_FEATURE_ENABLED/DISABLED (SECURITY), recording the transition, in one transaction with the write. The off state is a real screen at 200 for a page and 403 JSON with reason: tenant_feature_disabled for an API — and is shown only to a user whose role would otherwise allow the feature, because to anyone else it is untrue and leaks the tenant's licensing. SYSTEM_ADMIN bypasses the switch and the screen says so, so they cannot demo a feature the customer lacks. The 330-cell matrix earned its place twice. ⚠ It caught one defect and, more usefully, revealed its own blind spot: the snapshot measures the resolver, but the deleted gates lived outside it, so a blanket default_enabled = TRUE silently granted reports and skills_intelligence to 'Sam Cpmapny', which had no row for either and was therefore already denied — while the matrix reported "identical". Fixed by defaulting the two licensed features OFF (the only two ever gated; "no row" historically meant denied) and comparing the old gates directly. Final state: 319 of 330 cells identical, 11 changed as designed — all removals, at that one tenant, on those two features, with SYSTEM_ADMIN cells provably unmoved; the diff tool now enforces an explicit allow-list that permits removals only. ⚠ Also walked into DEF-004 and caught it: default_enabled is DATA, so setting it only in migration 11 left every fresh CI database defaulting both licensed features to TRUE while every developer machine read FALSE. Now in seed_rbac.sql too, guarded by test_the_seed_and_the_migration_agree_on_every_default. enabled_for_hr gains no consumer; removal path named in the route docstring (TD-17). 4,727 pytest · browser 105/105 · vacation 39/39, plus a full CI-style rebuild from schema.sql + seed_rbac.sql. / /
KAN-189 | 10 Aug 2026 | pytest 4,718 · browser 105/105 · vacation 39/39 | YES — see notes | All eight tasks. ADR-020 is the story: half-open [from, to) project-wide, so effective_to is the first day NOT covered. Read that way CFL-4's "one-day overlap" was never in the data — closing with effective_to = D and opening with effective_from = D is exactly adjacent — so the finding closed with a stated convention and no history rewritten, which is what the acceptance criteria asked for and the cheapest possible resolution. One date now drives both ends of the boundary, so they cannot drift apart. Verified against real Postgres, not mocks: daterange(from, to, '[)') && reports 0 overlapping periods in employee_org_assignments and 0 among SOLID_LINE relationships. DEF-42-2 closed, and further than scoped — the code fix stops new NULL-ended reporting lines, and migration 10 also repairs the 2 existing rows, deriving each end date from its successor's effective_from (recovered from data that was always there, not invented) and leaving any row with no successor honestly NULL rather than guessed. fmt_period() / fmt_last_day() are the only sanctioned renderers, with a grep-assert against printing effective_to raw. AC-185-07 delivered → KAN-185 closes. Verified CI-style on a throwaway database (schema.sql + seed_rbac.sql) so the column cannot be a dev-machine-only artefact. 4,718 pytest · browser 105/105 · vacation 39/39. ⚠ Two honest gaps, both stated rather than implied: (1) per-company window values are NOT delivered — they live on company_compensation_settings, a W1 table, and stubbing it early would make W1's own CREATE TABLE IF NOT EXISTS silently skip; _dating_window() is the single named seam. (2) DEF-004a raised — see the defect register. / /
KAN-190 | 10 Aug 2026 | pytest 4,774 · browser 110/110 · vacation 39/39 | YES — see notes | Families → levels → steps, with the ladder's dangerous number defended three ways. step_count counts increments ABOVE entry, so 5 yields six steps .0–.5 (the owner's own 2.0 … 2.5): a database trigger enforces the cross-table bound — TD-21 is closed, not accepted, because a step_no of 6 on a 5-step level is a pay point compounded six times, not a cosmetic error; step_total is computed once in the service so no template or JS repeats the arithmetic; and the form previews what the number means ("That gives 6 steps: 2.0 to 2.5") before it is saved. Verified in real Postgres: step 5 accepted, step 6 refused with the rule in the message. No default on step_count — column, API and form all require an answer, and the demo ladder deliberately has levels of 3, 5 and 2 steps to show why. Ordinal immutable once occupied (ADR-017b), counting historic assignments because a past record still points at the coordinate; renaming stays free; reducing steps below an occupied one is refused naming who is affected; and the empty state warns before the ladder is built. Two gates on one screen, and the third deliberately absent — read job_architecture:r (seeded to every role, so an employee can read their own step and the next), configure org_structure:w, and no write route uses job_architecture:w because that is roadmap authoring, not ladder editing (CFL-42-35, both halves, grep-asserted). The feature's label and description say what write actually grants, since a grant reading "Job Architecture: write" would mislead at the moment it is made. Tenancy enforced by composite FKs, not by service code — a cross-tenant family insert is refused by the database (verified), as is whitespace masquerading as authored content. Expectations are sparse and never inherited; level_steps() returns every step so an incomplete ladder cannot look complete; completeness is 4/9 with the gaps named, never a bare percentage. TestNoAssessmentColumnsOnTheLadder fails the build on any score/rating column in either the migration or schema.sql — the §14.5 / R-17 boundary made enforceable. STEP_NOT_ASSESSED is nullable and distinct from step 0 (A6), ready for KAN-191. First EP42 screen, and it calls KAN-204's shell primitives rather than reinventing them — announce(), escH(), the global focus ring, dialog semantics with focus return and Esc; asserted, because if the first of ten screens reinvents them all ten will. 4,774 pytest · browser 110/110 · vacation 39/39, plus a CI-style rebuild. ⚠ R-18 stands and cannot be automated away: nothing here can test whether the ladder text is any good, so "the ladder reads as a real description of the work" is on the Demo Gate's human list — and the demo seed leaves one level undescribed on purpose so the half-authored state is demoable. / /
KAN-191 | 10 Aug 2026 | pytest 4,828 · browser 110/110 · vacation 39/39 | YES — see notes | Two jobs kept apart because the product does: the mapping project (bulk, HR, title-driven — everyone gets a LEVEL) and step assessment (a manager's judgement against KAN-190's authored text, which A6 makes the only legitimate way a step is decided). One HR person assessing 146 people is a project nobody finishes; forty managers doing three or four each is a ten-minute task. STEP_NOT_ASSESSED is nullable and distinct from step 0 — verified in the browser: two placed people read "Step not yet assessed" while a third reads 1.3. The database keeps the history trustworthy, not service code: uq_eja_one_current (one current row) and excl_eja_no_overlap (EXCLUDE USING gist on daterange(from, to, '[)')), both verified against real Postgres — adjacent periods accepted, proving the half-open convention carries; second-current and overlap both refused. Bulk apply is previewed and never overwrites: dry run first, anyone already placed is skipped so a re-run cannot undo a deliberate correction, the whole apply is ONE transaction (a half-placed workforce is worse than an unplaced one — nobody can tell which half is real), one audit row with counts rather than 146, and it leaves the STEP unassessed. Nothing pre-selected on the assessment screen, not even the current step; the authored expectations appear at the point of choice with the step below for comparison; an undescribed step cannot be chosen at all. HR override needs a reason. employees.job_title untouched (ADR-017d). A real bug the mocked tests could not see: three audit calls passed a None entity id, which audit_service correctly refuses — every unit test passed because they patch the audit service wholesale, and it 500'd the first time a real request reached it. Found by clicking the screen; TestTheAuditRowsAreActuallyWritable now builds each row through the real validator. 4,828 pytest · browser 110/110 · vacation 39/39. ⚠ DEF-190-1 found by the Demo Gate and fixed — all five new dialogs rendered off-centre while every suite stayed green. / /
KAN-203 | 10 Aug 2026 | pytest 4,660 · browser 93/93 · vacation 39/39 |  | Both guards refuse ahead of every exemption, audited as ORG_CHANGE_SELF_ACTION_REFUSED (retention_class='SECURITY', outcome='FAILED'); the audit write is the one deliberate exception to ADR-009's join-the-caller's-transaction rule, because a refusal has no unit of work to join, and it can never turn a refusal into a 500. T-203-3 went wider than the ticket scoped it: the profile and directory already hid the affordance, but the org tree made every card draggable and — more seriously — list_pending and _step_approver_user_ids offered the subject a live Approve/Reject on their own move, in the inbox and the bell. That is the DEF-001/2/3 failure mode verbatim, so it was fixed here rather than logged: your own card is no longer draggable (it stays a drop target — moving somebody else under you is ordinary), the inbox omits requests about you, and the approver-resolution SQL excludes the subject so the badge count never includes it either. Named reproductions live in tests/test_transfer_entry_point.py §8 and were verified failing (18 tests) with the guards removed, not merely asserted green. CLAUDE.md invariant 2 + docs/ARCHITECTURE_REVIEW.md F32 landed in the same commit. 4,660 pytest · browser 93/93 · vacation 39/39. / /
KAN-204 | 10 Aug 2026 | pytest 4,680 · browser 100/100 · vacation 39/39 |  | All three landed, and T-204-1's instruction to verify rather than assume earned its keep: the audit confirmed the story's premise exactly — two focus rings in the entire product, no reduced-motion support, and the only live regions private to the move dialog. A1 is one --focus-ring token (with a lighter dark-theme value, because #2563eb on #0f172a is borderline against WCAG 1.4.11's 3:1) plus a global :focus-visible rule placed last in the stylesheet on purpose — it is 0,1,0, the same specificity as the three controls that set outline: none, so it wins by source order alone and moving it up the file silently breaks them. A test asserts that ordering and fails if a new outline: none is added after it. A3 is one polite + one assertive region, first in <body> (a region injected with its text is not reliably announced) and .sr-only rather than display:none (which removes it from the a11y tree and silences it — the failure that looks like success); the move dialog was migrated off its private pair, and a grep-assert over templates/ now fails the build if any screen declares its own. A9 is a universal block using .01ms, not 0s, because a zero duration fires no transitionend and code awaiting one hangs for ever; it caps the three infinite animations and leaves outline/colour cues alone. Also wired announce() into the directory's result count and empty state — a silent filter was a real gap, not a demo prop. Verified in a real browser, not only by asserting the CSS exists: 7 new checks prove the ring actually beats outline: none on the search box, that exactly one region pair is live, and that reduced motion applies in an engine honouring the query. 4,680 pytest · browser 100/100 · vacation 39/39. Documented as TECHNICAL_DOCUMENTATION.md §8b so an EP42 screen calls the primitive instead of reinventing it. / /
KAN-207 | 10 Aug 2026 | pytest 4,882 · browser 110/110 · vacation 39/39 | YES — see notes | The distinction holds in the schema, not just the prose: the expectation says what step 1.2 means here for anybody; the roadmap says what you specifically need to do. Versioned, never overwritten — a new version supersedes the previous one inside the same transaction so uq_esr_one_live can never see two live rows, and the old one stays readable; from/target coordinates and the author's name are denormalised on purpose, because resolving them live would silently re-target every historical roadmap the moment somebody is promoted. Acknowledgement records a DISCUSSION, not agreement (CFL-42-50): the button reads Confirm we discussed this, the state reads "Discussed on 14 March", the audit action is STEP_ROADMAP_DISCUSSION_CONFIRMED and its reason says explicitly that it is not agreement — only the subject may confirm, it is idempotent, and an unconfirmed roadmap is still live and blocks nothing, with the follow-up surfaced to the manager instead. The employee is notified, once, in-app — the owner's overrule of the BA's and UX's "no", because a roadmap nobody knows about delivers zero transparency; no email, retires on view (an FYI must not sit in the bell like an approval), sent after the commit, and carrying no step number and no pay. /my-ladder is main nav on job_architecture:r, seeded to every role — visible to the employee, not optional. ⚠ Closed a KAN-190 gap that was missed: the step-disclosure switch (companies.display_step_to_employee, default TRUE) was in KAN-190's criteria and never built; it is added here because this is the first surface that consumes it. With it off, A2 option (b) — the roadmap reads in full as "What the next set of expectations looks like", with no step number and no "you are here". No ratings, scores, readiness or likelihood anywhere, in either the migration or schema.sql — that boundary is what keeps this out of GDPR Art. 22 / EU AI Act territory, and the test parses the function body rather than grepping, because the docstring names the ban in order to state it. Verified in a browser end to end: a manager blocked from writing for an unassessed report (with the reason), 1.3 → 2.0 correctly crossing into the next level, the bell badge appearing for the employee, and the wording correct in both the pre- and post-confirmation states. 4,882 pytest · browser 110/110 · vacation 39/39. ⚠ NOT Ready until a human reviews the copy against R-17 — the Architect declined to certify, correctly: the risk is whether it reads as expectations rather than an assessment, and no test can see that. The SPM owns that review. / /

## Decisions
Decisions
Owner decisions. "In his own words" is filled where the decision was recorded verbatim.
ID | Headline | In his own words | Detail
D-004 | / EP28 / Security Hardening (Architecture Review) / KAN-148 · KAN-149 · KAN-150 · KAN-151 · KAN-152 · KAN-153 / 🟡 In progress · ⏸ deferred to final stage S5 (D-004; KAN-153 excepted) / |  | No verbatim block — see BACKLOG.md for context.
D-006 | 2026-08-09 — recorded verbatim, because this is exactly the decision somebody > re-litigates six weeks from now. | I want a full performance-management capability (cycles, goals, calibration) a detailed performance requirement impmlemation" and "go ahead with full implemenation cycle as Product owneer accepting… | Context: the SPM sized a performance input — a manager-entered band per employee per cycle, 2 stories, ~2–3 weeks, no delay — against full performance management — ~20–25 stories, 12–16 weeks, sequenced first, pushing the hike cycle out by roughly a quarter — and recommended (a) with Confidence High. Options considered: (a) performance input inside EP43 · (b) full performance management as EP44. Decision: (b). His words: "I want a full performance-management capability (cycles, goals, calibration) a detailed performance requirement impmlemation" and "go ahead with full implemenation cycle as Product owneer accepting the delay." Rationale: his, not the SPM's. He named the three things option (b) contained, so this is a considered choice against a stated cost, not a misread — and he then accepted the cost in his capacity as product owner and in those words. Impact:…
D-007 | 2026-08-10 — initiator ≠ approver is ACCEPTED AS-IS by the owner. | This is ok because on top of Ravi we do not have 2 levels of managers | Context: KAN-203 closed subject ≠ initiator and subject ≠ decider (DEF-42-4 / DEF-42-5). The other half of DEF-42-5 — initiator ≠ approver — was left open by design and scheduled money-scoped in KAN-198. Engineering disclosed the live consequence plainly: today an HR_ADMIN can raise a transfer for somebody else and then approve it themselves, with no second person involved. Decision: the owner accepts it and does not want it closed. His words: "This is ok because on top of Ravi we do not have 2 levels of managers. So that's ok." Rationale: his. The chain above an individual contributor is not deep enough in this organisation for a second approver to be a meaningful control on a placement move; requiring one would add a step that no real person is available to take. Status: the concern was raised once, the owner reaffirmed, engineering proceeded. Not re-litigated. …
D-008 | ## SEQUENCING — where performance management goes (D-008: Option C — ⚠ SUPERSEDED BY D-010, sequential) |  | No verbatim block — see BACKLOG.md for context.
D-009 | 2026-08-10 — the three shape questions for performance management. |  | Context: EP44's requirements exercise opened under D-008 (Option C). Three choices changed the shape of the build rather than its wording, so they were put to the owner with a recommended default each and an explicit note that none of them blocked. / # / Question / Default put to him / His answer / /---/---/---/---/ / 1 / Cycle cadence, and is it tied to the pay round? / Annual, mid-term check-in, independent of the pay round / "Once a year" — default confirmed / / 2 / Is probation a real cycle or just a label? / Just a label; no probation cycles, no probation screens / "No probation a real cycle" — read as no probation as a real cycle, i.e. default confirmed / / 3 / Does an employee see their manager's written assessment? / Yes, after the manager submits / "Yes" — default confirmed / ⚠ On (2), the reading is recorded because the phrasing was ambiguous. "No…
D-010 | 2026-08-10 — performance is built FIRST; compensation follows it. | Proceed with Performance Review development | His words: "Proceed with Performance Review development. I'll review and sign off the roadmap wording separately. Compensation can follow after the performance module is completed." This supersedes the parallelism in D-008 (Option C). Option C ran performance P0–P2 alongside compensation W1–W3, on the assumption of extra capacity. The order is now sequential: the performance module completes, then compensation W2–W4. Read as: performance entirely before the remaining compensation waves — not "performance first within the parallel plan". Flagged, because the two readings differ by about a quarter. He has also decoupled the KAN-207 copy sign-off from the critical path by taking it himself, which is what lets this proceed today. What it costs, stated once and not re-litigated: EP42 W2 was the minimum shippable slice — pay markets, what each step is worth, and…

## Defects
Defects
The register. "Accepted" means a known behaviour the owner chose to keep, not an open bug.
ID | State | Severity | Description | Owner / route
DEF-42-4 | Fixed | Critical | ✅ FIXED in KAN-203 (10 Aug 2026). _can_initiate_for never compares the initiator to the subject. It returns True for any holder of HR_ADMIN / PORTAL_ADMIN / SYSTEM_ADMIN regardless of who the subject is, including themselves. CLAUDE.md's headline org-change invariant says "An individual employee can NEVER initiate their own move"; the rule as implemented beneath it grants admins a blanket exemption. The code matches the detailed rule and violates the headline. The exemption exists so HR can move other people; it was never meant to cover acting on oneself. The headline is right and the code… | Pre-existing, raised against EP27. Fixed in KAN-203, in W0, not deferred to W3 — the exposure is live today and the guard has no EP42 dependency. CLAUDE.md reworded in the same commit (Architect owns the file).
DEF-42-5 | Fixed | Critical | ✅ Subject≠decider FIXED in KAN-203 (10 Aug 2026); initiator≠approver still open in KAN-198. decide() never compares the decider to the subject or the requester. It checks the decider against the step and the company, and nothing else. Combined with DEF-42-4, one HR_ADMIN can raise a position change for themselves and approve it end to end on the seeded default chain, today. After KAN-196 that becomes a self-approved pay rise. | Pre-existing, raised against EP27. Subject≠decider fixed in KAN-203 (universal). Initiator≠approver is CLOSED AS ACCEPTED for placement moves by owner Decision D-007 (10 Aug 2026) — the chain above an IC is not deep enough here for a second approver to be a real control. It is documented, accepted behaviour, not an open defect, and must be disclosed at the top of any gate walkthrough touching…
DEF-004a | Open | Medium (1 employee today;… | One employee has TWO current DOTTED_LINE managers, and the product can only ever show one of them. Found by the daterange(from, to, '[)') && non-overlap check run against real Postgres while verifying KAN-189 — the only overlapping pair in the whole database, both rows is_current = TRUE and open-ended from the same day. _EMP_SELECT reads the dotted line with a LATERAL … LIMIT 1, so the second relationship is invisible everywhere in the UI: it is real data that no screen can show and no user can discover or remove. Not caused by, and not fixable in, KAN-189 — the org-change engine only ever… | Raised 10 Aug 2026 during KAN-189 verification. Deliberately NOT fixed there — silently deleting one row would destroy information, and silently showing both would change a product behaviour nobody has asked to change. Needs the owner's call on multiple dotted lines, then either the EXCLUDE constraint from TD-22 (which ADR-020's convention makes a drop-in) or a UI that shows all of them.
DEF-42-1 | Open | High | The CSV employee importer cannot write a valid employment_type, and fails silently when it tries. EMPLOYMENT_TYPES contains FULL_TIME (which the DB CHECK rejects) and omits PERMANENT (which it requires); a blank cell defaults to FULL_TIME; the resulting CHECK violation is caught and the row is marked SKIPPED with no reason surfaced to the user — the DEF-002 shape. | Pre-existing, raised against EP21. Not absorbed into EP42 — EP42 did not break it, and burying it would misattribute the cause. P1, scheduled in S2, before KAN-195 starts. EP42 keys its exclusions and FTE handling on employment_type and bulk import is the only bulk path.
DEF-42-2 | Open | Medium | manager_relationships rows are closed without an effective_to — 2 such rows in the dev database. The pattern EP42 was told to copy for effective dating is undated on its closing side. | Fixed inside KAN-189. Cheap to fix in the same change; expensive once copied into three new tables.
DEF-42-3 | Open | Medium (data) | employees.gender is NULL for 100% of the seeded population, and there is no admin-facing collection path beyond registration and CSV. | Product consequence, not a code fix: Check B has nothing to run on and would report "insufficient gender representation" for every group in every tenant. UAT fixtures must supply it; Check B must not be demoed on seed data; and the owner should know, when answering OQ-3, that he may be buying a check that has no data.

## Questions
Open questions
Whether each has been answered. An answered question keeps its row so the trail survives.
ID | State | Context from the backlog
OQ-1 | Answered | / ⬜ KAN-192 / As a manager or HR admin, I want step advancement to be an explicit recorded decision taken at a review, which proposes the matching pay adjustment rather than applying it. (R6 · D3.4 · A1 — OQ-1 CLOSED: confirmed not automatic) / Step advancement is an explicit audited action carrying a mandatory review_context — PROBATION_REVIEW · MID_TERM_GOAL_REVIEW · PERFORMANCE_REVIEW ·…
OQ-2 | Open | 1. Seven questions still need the product owner's answer — OQ-2 (three visibility-matrix cells), OQ-4 (the
OQ-3 | Answered | 0. Amendment A1 (2026-08-09) closed OQ-1 and OQ-3. OQ-1 confirmed — progression is not automatic —
OQ-4 | Open | 1. Seven questions still need the product owner's answer — OQ-2 (three visibility-matrix cells), OQ-4 (the
OQ-5 | Answered | > OQ-5 CLOSED — base salary only (his words "at this point" convert it into an extensibility rule, not a
OQ-6 | Open | what the increment applies to as well as the record's shape), OQ-6 (multi-currency — less pressing, since
OQ-7 | Open | an absolute per-market reference never crosses currencies), OQ-7 (default exposure off), OQ-8 (works
OQ-8 | Answered | OQ-8 (works councils) — ✅ ANSWERED by the owner, 10 Aug 2026: NO. Asked whether performance-related pay
OQ-9 | Open | councils), OQ-9 (segregation of duties, extended to cover the initiator and SYSTEM_ADMIN). All carry a
OQ-10 | Answered | > OQ-10 — ✅ ANSWERED 10 Aug 2026: introduce a submission deadline. His words: *"Introduce a
OQ-11 | Answered | > OQ-11 — ✅ ANSWERED 10 Aug 2026: three values. His words: *"Achieved / Partially achieved / Not